## COVER
ANTRAC / WELL LAND – CONSOLIDATED OPERATIONS & PROCUREMENT LOG
Period: 26 Jan 2026 – 22 Mar 2026 ¦ Groups: BF Machine & Diesel Ops · WL Logistic Group · AH Group R&M ¦ Compiled: 22 Mar 2026 ¦ Prepared for: Ali Mushthaq Ibrahim – GM Logistics
PERSONNEL & ROLES
Ali Mushthaq Ibrahim | GM Logistics & Heavy Vehicles | Well Land Investment Pvt Ltd (Antrac Group) | End-to-end SCM, machine ops, logistics across BF, MF, Goidhoo & vessel fleet. This workbook is his master log.
Mohamed Hameed | Director / BOD | Antrac Holding Group | Principal decision-maker. Escalation authority across all operations and subsidiaries.
Abdul Hannan (AH) | Director / BOD | Antrac Holding Group | Operational escalation authority. Final approver on site staffing and vessel movements.
Sampath | Project Manager | Antrac – Based at Bodufinolhu (BF) | Manages BF & Muthaafushi (MF) site operations. Primary field reporter.
Janaka | Senior Supervisor | Antrac / Well Land – Based at Thilafushi | Procurement, parts sourcing, fleet requisitions, dispatch coordination.
Ahmed Ziyad Hassan | PFSO – Port Facility Security Officer & Logistics / Parts Coordinator | Petroleum Link MPL & Well Land – Malé | Port security. Also assists logistics/parts coordination in Malé. Ferry dispatches, part collection from Malé, inventory receipts.
Ndirangu Nginga | Mechanic | On-site – BF / MF | Machine repairs and maintenance. Field mechanic.
Nashwan | Operations Coordinator | Antrac Ops | Vessel and dhoni logistics, movement coordination.
Dhanushka | Repair & Maintenance Manager | AH Group | Manages marine and barge maintenance team. Marine mechanic supervision.
Ziyadh (Ziyad) | PFSO – Port Facility Security Officer | Petroleum Link (PLK) / MPL | Port security. Also assists logistics/parts coordination in Malé.
Gasim | Assistant Manager Cargo Operations , Antrac | WL Logistic Group
Shifan | Terminal Manager MPL | AH Group R&M
WORKBOOK STRUCTURE
1. COVER | This page – roles, structure, status legend.
2. ACTIVITY LOG | Chronological log of all events from all 3 WhatsApp groups (machine status, logistics, decisions, escalations).
3. MATERIAL REQUESTS | All material/parts requests raised at site level (Sampath / informal WhatsApp requests, no PO number).
4. PURCHASE REQUESTS | All formal purchase requests logged by Janaka (Antrac & WellLand series) + site informal requests – consolidated master register.
5. RECEIPTS | All confirmed goods received at site or in transit.
6. INCIDENTS & ISSUES | Machine breakdowns, failures, damage events, stock discrepancies.
7. OPEN ITEMS | All unresolved actions requiring follow-up – your daily chaser list.
8. DIRECTED AT MUSHTHAQ | ⭐ YOUR PERSONAL ACTION SHEET – all messages/requests directed at you across all groups. Log your response and mark status here.
STATUS LEGEND
🔴 OPEN / PENDING / NOT ACTIONED | Requires immediate attention
🟢 CLOSED / DONE / RECEIVED | Completed – no further action
🟡 IN PROGRESS / PARTIAL / TRANSIT | Underway – monitor
⚪ UNKNOWN / UNCONFIRMED | Status not confirmed – follow up
🟠 URGENT | Priority flag on priority column
🟣 DIRECTED AT MUSHTHAQ | Personal action item

## ACTIVITY LOG
CONSOLIDATED ACTIVITY LOG – All Groups – 26 Jan 2026 to 22 Mar 2026
# | Date | Time | Source Group | Reported By / Role | Category | Location | Description / Detail | Action Taken / Response | Status | Follow-Up Required
1 | 26-Jan-26 | 18:00 | BF Machine & Diesel | Mohamed Hameed – Director | ADMIN | Group | Mushthaq introduced as new GM Logistics & Heavy Vehicles | — | DONE
2 | 26-Jan-26 | 18:07 | BF Machine & Diesel | Sampath – PM | MATERIAL REQUEST | BF | 10-item materials list raised (6 URGENT): Perspex sheet ×1, Silicone ×2, Silicone gun ×1, Large D-shackle ×1, Diesel pump ×1, Grease gun ×1 (all URGENT); Grease, O-ring box, Radiator coolant, Bucket teeth & pins (normal) | Noted; follow-ups through Feb | PARTIALLY ACTIONED | Check D-shackle, grease, coolant dispatch
3 | 26-Jan-26 | 18:07 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF/MF | BF – Komatsu: coconut planting, slow movement. Kobelco: boom pin today, bucket pin pending materials. SK 235: OOO – starter motor to Malé. PC50: planting. Dump Truck: awaiting hose (sent 22 Jan). MF – Dump Truck: oil leakage | — | NOTED | SK235 repair status; MF DT fix
4 | 27-Jan-26 | 11:13 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF/MF | Kobelco boom & bucket pin repaired – coconut planting. Komatsu planting, slow movement. SK235 OOO – motor sent to Malé today. PC50 planting. Dump truck awaiting hose. MF DT: oil leakage, mechanic to go with Komatsu | Mohamed Hameed: Thanks | NOTED
5 | 27-Jan-26 | 11:34 | BF Machine & Diesel | Sampath – PM | LOGISTICS | BF | 2 new brake hoses at site. Waiting for hydraulic hoses. Hope recovered today. | Mohamed Hameed: Sending by ferry, collect | IN PROGRESS | Confirm hose received
6 | 27-Jan-26 | 19:01 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF | Hydraulic needs to be filled. Tom [mechanic] to check. | — | UNKNOWN | Confirm hydraulic filled
7 | 28-Jan-26 | 17:10 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF/MF | Komatsu: diesel air lock – diesel filter needed. Kobelco: hired to Evosun. SK235 OOO. PC50 planting. Dump Truck: hired to Evosun. MF DT: oil leakage, mechanic with Komatsu | Mohamed: Komatsu also needs fix | NOTED | Diesel filter for Komatsu
8 | 29-Jan-26 | 08:01 | BF Machine & Diesel | Sampath – PM | MATERIAL REQUEST | BF | Re-raised same 10-item list; asked for update | — | PENDING | All 10 items status
9 | 29-Jan-26 | 10:46 | BF Machine & Diesel | Janaka – Sr. Supervisor | MATERIAL STATUS | Thilafushi | Items 4 (D-shackle), 7 (Grease), 9 (Coolant) available in Thilafushi | — | AVAILABLE – dispatch pending | Dispatch to site
10 | 29-Jan-26 | 14:57 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF/MF | Komatsu sent to MF at 14:00 with mechanic. Kobelco: Evosun till 14:00, then planting. Dump Truck hose burst 14:45 – Evosun mechanic to help. MF DT: mechanic went with Komatsu | — | NOTED | Dump truck hose repair confirmation
11 | 29-Jan-26 | 15:20 | BF Machine & Diesel | Sampath – PM | MATERIAL REQUEST | BF | Need brake oil and Adblue | Janaka: Volvo sent 1 Jan with 20L coolant & Adblue – check on site | PARTIALLY RESOLVED | Adblue confirmed (PAL ADF). Brake oil still needed.
12 | 30-Jan-26 | 20:34 | BF Machine & Diesel | Sampath – PM | LOGISTICS | Malé → BF | Mohamed sending hose to Malé; cannot reach Alam | Mohamed: Spoke to Aalam, he will collect from ferry | IN PROGRESS | Confirm collected
13 | 31-Jan-26 | 06:29 | BF Machine & Diesel | Mohamed (M +960791-4847) | LOGISTICS | BF | Hose sent via Atoll Cute Crown | — | DISPATCHED | Confirm receipt
14 | 31-Jan-26 | 12:41 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF | Only Kobelco working. All others broken. Site work and tree unloading impacted. Starter motor query raised. | @Ahmed Ziyad on it | CRITICAL – RESOLVED by Feb
15 | 31-Jan-26 | 17:35 | BF Machine & Diesel | Sampath – PM | RECEIPT | BF | Received: 6 filters, Manual pump, O-ring box, Small grease gun, 2 Silicone, Silicone gun, 2 Lifting belts | — | RECEIVED
16 | 01-Feb-26 | 13:10 | BF Machine & Diesel | Ahmed Ziyad Hassan – Logistics | PROCUREMENT | Malé | Electric Diesel Transfer Pump identified (OLM #3007811) | — | PROCUREMENT IN PROGRESS | Confirm if ordered and delivered
17 | 04-Feb-26 | 12:21 | BF Machine & Diesel | Ahmed Ziyad Hassan – Logistics | RECEIPT | BF | Goods via Atoll Cute Crown: Starting Motor, Hose, O-ring set (Dump Truck), Filters | Sampath: @Mohamed pls collect | DISPATCHED | Confirm collected
18 | 04-Feb-26 | 16:15 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF – Kobelco | Starter motor to be fixed today. MF O-ring fix tomorrow | — | IN PROGRESS | Confirm MF O-ring fixed
19 | 04-Feb-26 | 16:19 | BF Machine & Diesel | Mechanic (+91 99947 41533) | INSPECTION | BF – Kobelco | Cracks on steel bush – temporary weld repair. Cabin removal needed for permanent fix. Can work slowly. | Sampath: recommended send to Malé | TEMPORARY FIX | Permanent bush repair pending
20 | 06-Feb-26 | 09:06 | BF Machine & Diesel | Sampath – PM | RECEIPT | BF | Received: Fuel pump, Grease gun, 2 AC machines, Washing machine, AC gas R410A, Hydraulic barrel | — | RECEIVED
21 | 08-Feb-26 | 12:17 | BF Machine & Diesel | Sampath – PM | LOGISTICS | BF → Malé | Starter motor + hydraulic hose sent to Malé with mechanic | — | DISPATCHED | Confirm repair complete
22 | 08-Feb-26 | 12:18 | BF Machine & Diesel | Sampath – PM | PERSONNEL | Goidhoo | @Janaka arrange dump truck tools. Abdul Hannan: 1 excavator driver to Goidhoo. Janaka: Yes. Sampath: send via LCT | — | ARRANGED | Confirm driver arrived
23 | 09-Feb-26 | 11:54 | BF Machine & Diesel | Mohamed Hameed – Director | DIRECTED @ MUSHTHAQ | BF | @Mushthaq (Well Land) – Ndirangu hasn't gotten help with jetty booking. What is the situation? | Mushthaq: Jackson on way to ferry, reaching 12pm | CLOSED
24 | 10-Feb-26 | 07:59 | BF Machine & Diesel | Sampath – PM | MATERIAL REQUEST | BF | Need grease gun coupler (NPT 1/8 in. type, ACE brand image forwarded) | — | OPEN | Grease gun coupler procurement
25 | 10-Feb-26 | 08:37 | BF Machine & Diesel | Mohamed Hameed – Director | MAINTENANCE | MF | Send mechanic to Muthaafushi urgently to fix dump truck | Sampath: Already arranged | ARRANGED | Confirm fix done
26 | 12-Feb-26 | 08:48 | BF Machine & Diesel | Sampath – PM | MATERIAL REQUEST | MF | MF requirements: Diesel hose for manual pump (20ft), Grease gun, Grease, Grease nipple (Komatsu 350), Solenoid (Komatsu 350) | — | OPEN – Multiple items unresolved | Check each item
27 | 13-Feb-26 | 16:35 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Dump Truck | Drum truck hydraulic hose burst. Sending to Malé tomorrow. | — | IN PROGRESS | Hose repair/return ETA
28 | 14-Feb-26 | 12:01 | BF Machine & Diesel | Ahmed Ziyad Hassan – Logistics | LOGISTICS | Malé → BF | Sent hose via Moosabe vessel | Sampath: Thanks | DONE
29 | 15-Feb-26 | 11:44 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Komatsu | Small hole in steel fuel pipe. Sent to Thuladhoo for gas welding. | Mushthaq: keep updated; replace if not usable | IN PROGRESS | Welding result – replace?
30 | 15-Feb-26 | 22:22 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Excavator | Hydraulic hose burst on excavator | AH: Which one? | RESOLVED – spare used
31 | 16-Feb-26 | 07:01 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF | Hose fixed with spare (bought for dump truck). Broken pipe sent to Malé with Rizwan driver. | Mushthaq: confirmed with whom? AH: Ziyadh collect | FIXED | Confirm new spare procured
32 | 16-Feb-26 | 07:02 | BF Machine & Diesel | Abdul Hannan – Director | OPERATIONS | BF | 2,750 tons unloaded. 5–6 hrs remaining. | Sampath: need another 5-6 hrs | IN PROGRESS
33 | 19-Feb-26 | 07:58 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF/MF | @Mushthaq – Morning. Materials needed: Komatsu: Hydraulic oil, Diesel filter, Oil filter, Solenoid, Grease, Grease gun, Cotton waste. BF Dump Truck: Brake oil + all service filters. ETA on ordered items? | — | OPEN – Multiple items | Coordinate with Janaka for ETA
34 | 19-Feb-26 | 08:01 | BF Machine & Diesel | Abdul Hannan – Director | OPERATIONS | Thulhaadhoo → BF | 6 diesel barrels from Thulhaadhoo – empty and return to Kunbe Mohamed house. Diesel needed for both sites. | Sampath: Need diesel; requested 4000L | IN PROGRESS | Confirm diesel delivered to BF + MF
35 | 19-Feb-26 | 11:03 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Komatsu | Komatsu having issues (video). Mechanic to attend. | Ndirangu: Fixed (12:15) | FIXED
36 | 19-Feb-26 | 17:34 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Dump Truck | Small damage in dump truck hydraulic hose. Won't send to sea – risk of burst. | Mushthaq: How to fix? Sampath: Sending hose to Malé, use MF DT | IN PROGRESS | Confirm hose repaired
37 | 20-Feb-26 | 06:45 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF | @Mushthaq (Well Land) @Janaka – Can you send Adblue please? | 4 Adblue cans received at BF on 02-Mar-26 | CLOSED
38 | 21-Feb-26 | 10:39 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF | Two burst hoses to Malé. Total 2 hoses with Hannan Sir. | AH: The one I brought given to Ziyadh | IN TRANSIT | Confirm all repaired
39 | 21-Feb-26 | 17:46 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF – Kobelco | @Mushthaq – Kobelco cannot operate. Mechanic says water leaking through gasket. | Monitoring; gasket sourced; Kobelco fixed by 03-Mar | CLOSED
40 | 22-Feb-26 | 10:58 | BF Machine & Diesel | Sampath – PM | OPERATIONS | BF → MF | Sending Komatsu high bed + drum truck to MF. BF DT and excavator grounded. | AH: Keep machines in BF until repaired | GROUNDED | BF machines under repair
41 | 22-Feb-26 | 16:05 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF – Komatsu | @Mushthaq – Another hose burst on Komatsu. Sending to Thuladhoo/Musa then Malé tomorrow. Total 3 hoses burst. | Hoses sent via Atoll Cute King 23-Feb | CLOSED
42 | 23-Feb-26 | 19:32 | BF Machine & Diesel | Sampath – PM | OPERATIONS | BF | Evosun requesting Komatsu for concrete work. Hold MF machinery move? | Mohamed Hameed: Yes. Janaka arranging mechanic to fix MF. | APPROVED
43 | 24-Feb-26 | 15:04 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF – Dump Truck | @Mushthaq – Dump truck operator: oil viscosity high, needs immediate service. Safe to operate? | Mushthaq: NOT SAFE. DO NOT OPERATE. Sent Volvo A40D checklist PDF. | OPEN – Service pending | Arrange service ASAP
44 | 24-Feb-26 | 15:33 | BF Machine & Diesel | Mushthaq | DIRECTED @ MUSHTHAQ | BF – Dump Truck | Sent Volvo A40D Immediate Troubleshooting Checklist PDF to Sampath for inspection. | Sampath: Noted | PENDING – Checklist not returned | Completed checklist to be received back
45 | 24-Feb-26 | 16:15 | BF Machine & Diesel | Mushthaq | DIRECTED @ MUSHTHAQ | BF – Stock | Hydraulic oil barrel: 209L received, only 50-60L found. Mushthaq: nobody to use anything without informing me. | Sampath: Ok | CONTROL ISSUE – Log enforced | Usage log mandatory from here
46 | 25-Feb-26 | 10:05 | BF Machine & Diesel | Sampath – PM | RECEIPT | BF | Received package (Komatsu solenoid + Kobelco gasket per Mohamed Hameed). | — | RECEIVED – WRONG PART | Solenoid socket mismatch – correct part needed
47 | 25-Feb-26 | 10:30 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF – Komatsu 350 | Wrong solenoid received (pilot block). Required: solenoid + Allen screw size 4 ×2, on top of hydraulic pump. | Janaka: pilot block; checking. Send sample to Malé. | OPEN | Correct solenoid – need OEM part number
48 | 28-Feb-26 | 12:26 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF | @Mushthaq – Rock boulder shipment arriving 4 March. Two excavators must be fixed immediately. | Mushthaq: I am following this | OPEN – Escalated | Both excavators to be ready by 4 Mar
49 | 28-Feb-26 | 16:17 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF – Komatsu | Solenoid NOT received. Engine top cover cracked (250×850mm) – needs repair. | Mushthaq: I am looking into this | OPEN | Solenoid + engine cover repair
50 | 28-Feb-26 | 16:42 | BF Machine & Diesel | Mohamed Hameed – Director | DIRECTED @ MUSHTHAQ | BF | @Mushthaq (Well Land) – really we need to do your responsibility properly. | Mushthaq: I need to know what is happening. Those who cannot take responsibility I urge them to resign. | ESCALATED | Improve communication flow
51 | 28-Feb-26 | 17:07 | BF Machine & Diesel | Janaka – Sr. Supervisor | LOGISTICS | BF ← Malé | Solenoid to arrive BF tomorrow. Sampath send 380 excavator cover to Malé tomorrow. | — | IN TRANSIT | Confirm both items
52 | 01-Mar-26 | 09:07 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Komatsu | One bucket tooth removed (photo) | — | OPEN | Tooth replacement
53 | 01-Mar-26 | 11:30 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF | @Mushthaq @Ahmed Ziyad Hassan – Is it possible to send engine cover tomorrow? | Ahmed: Yes, sure | ARRANGED | Confirm cover dispatched
54 | 02-Mar-26 | 10:02 | BF Machine & Diesel | Sampath – PM | RECEIPT | BF | Received: Kobelco 10 filters (5 oil+5 fuel), Komatsu Solenoid, 1 belt (Goidhoo), Adblue ×4 cans | — | RECEIVED | Confirm solenoid compatible
55 | 02-Mar-26 | 10:04 | BF Machine & Diesel | Sampath – PM | MAINTENANCE | BF – Komatsu | Solenoid socket does not match existing. Direct connection? | Mushthaq: Do NOT recommend. Get mechanic + OEM part number. | OPEN | Correct solenoid still required
56 | 03-Mar-26 | 08:45 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF – Komatsu | @Mushthaq – Komatsu cannot work. Needs oil + diesel filter. No Komatsu filters on site. Goidhoo has fuel filter only. | Mushthaq: Okay. Coordinate Goidhoo to send fuel filter today. | CLOSED – Fuel filter dispatched | Oil filter still needed
57 | 03-Mar-26 | 12:25 | BF Machine & Diesel | Sampath – PM | LOGISTICS | BF → Malé | 2 bags (filters) sent via Atoll Cute Crown. @Mohamed collect. | Mohamed: Ok | DISPATCHED | Confirm collected
58 | 03-Mar-26 | 14:19 | BF Machine & Diesel | Ndirangu Nginga – Mechanic | MACHINE STATUS | BF | Kobelco now working. Komatsu waiting for filters. | — | PARTIAL | Komatsu filter service
59 | 03-Mar-26 | 22:17 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF – Komatsu | Filters changed. Not working well. Mechanic tomorrow. | — | IN PROGRESS | Mechanic assessment
60 | 04-Mar-26 | 11:16 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF – Komatsu | Komatsu working now (video). | — | WORKING
61 | 04-Mar-26 | 11:29 | BF Machine & Diesel | Sampath – PM | MACHINE STATUS | BF | Both Kobelco and Komatsu working now. | — | WORKING
62 | 07-Mar-26 | 08:58 | BF Machine & Diesel | Sampath – PM | INCIDENT | BF – Komatsu | Komatsu hose burst again. Trying to fix with available hose. Kobelco working. | Mushthaq: Contingency? Sampath: Kobelco covering. | IN PROGRESS | Send burst hose for replacement
63 | 15-Mar-26 | 09:12 | BF Machine & Diesel | Mushthaq | OPERATIONS | BF | Both machines wanted in working condition. Send hose to confirm and get replacement. | Sampath: Sure, sending tomorrow | IN PROGRESS | Confirm hose sent and replacement received
64 | 15-Mar-26 | 07:53 | BF Machine & Diesel | Sampath – PM | DIRECTED @ MUSHTHAQ | BF – Kobelco | @Mushthaq – Hydraulic leak in Kobelco arm jack. Need jack seal. Also: Hydraulic 20L, Engine oil 65L, Coolant 10L, Adblue 40L, Oil+Fuel filters for PC50. | Mushthaq: Yes. We are on it. | IN PROGRESS | Jack seal + PC50 filters dispatched?
65 | 15-Mar-26 | 15:06 | BF Machine & Diesel | Mohamed Hameed – Director | OPERATIONS | BF → MF | Send 2 good machines (1 high bed + 1 low bed excavator + truck) to MF for rock boulder work before monsoon. | AH: Organizing. Sampath: LCT expected tomorrow. | ARRANGED | Confirm LCT arrived; machines at MF
66 | 17-Mar-26 | 18:31 | BF Machine & Diesel | Sampath – PM | MATERIAL REQUEST | BF | Follow-up on jack seal, fluids, PC50 filters | Mushthaq: Yes. We are on it. | IN PROGRESS | Confirm items dispatched
67 | 22-Mar-26 | 13:47 | BF Machine & Diesel | Janaka – Sr. Supervisor | MAINTENANCE | BF – PC50 | Request clear photos of PC50 filters – previous pics too blurry to identify correct parts. | Sampath: @Ndirangu do needful | IN PROGRESS | Ndirangu to send clear photos
68 | 22-Mar-26 | 14:24 | BF Machine & Diesel | Ndirangu Nginga – Mechanic | MAINTENANCE | BF – PC50 | Osaka oil & fuel filter photos sent for Kubota 50 | — | DONE – PENDING SELECTION | Janaka to select + order
69 | 22-Mar-26 | 13:58 | BF Machine & Diesel | Mohamed Hameed – Director | OPERATIONS | MF | Send Komatsu low bed to MF for rock boulder work – good low tide window. | AH: Organizing | IN PROGRESS | Confirm Komatsu dispatched to MF
70 | 22-Mar-26 | 14:01 | BF Machine & Diesel | Abdul Hannan – Director | LOGISTICS | Maniyafaru | Push Nasru to load items from Maniyafaru tomorrow morning ASAP | — | PENDING | Confirm Nasru loading 23 Mar
71 | ~24-Feb-26 | 10:47 | WL Logistic Group | Mohamed Hameed – Director | LOGISTICS | WL Group | Food logistics request raised. Nashwan given client contact first. | — | ACTIONED | Follow-up on food supply proposal outcome
72 | ~24-Feb-26 | 10:49 | WL Logistic Group | Mohamed Hameed – Director | BUSINESS DEV | WL Group | Suggestion: propose food supply service to the food logistics client as well. | — | OPEN | No follow-up on food supply proposal recorded
73 | ~24-Feb-26 | 10:51 | WL Logistic Group | Nashwan – Antrac Ops | VESSEL OPS | Dhidhoo | Dhoni arriving Thilafushi to fuel today, then departing to Dhidhoo this evening. Client wants food delivery tomorrow. | — | IN PROGRESS | Confirm food delivery completed at Dhidhoo
74 | ~24-Feb-26 | 17:07 | WL Logistic Group | Nashwan – Antrac Ops | MAINTENANCE QUERY | TUG 1 | Who is looking after TUG 1 repair and maintenance? (no response same day) | Hannan (25 Feb): Call Ziyadh pls | OPEN – Redirected | Mushthaq to clarify TUG 1 R&M ownership and confirm with Ziyadh
75 | 25-Feb-26 | 10:00 | WL Logistic Group | Nashwan – Antrac Ops | MAINTENANCE QUERY | TUG 1 | Follow-up on TUG 1 R&M question: ??? (unanswered) | Hannan: Call Ziyadh pls | OPEN | Confirm Ziyadh contacted re TUG 1
76 | (Undated ~Mar) | 12:06 | AH Group R&M | Mohamed Hameed – Director | PERSONNEL | Marine Site | Marine mechanic joining today. Will work under Dhanushka (R&M Manager) at site. | 2 thumbs up from group | ACTIONED | Confirm mechanic arrived at site
77 | (Undated ~Mar) | 12:09 | AH Group R&M | Mohamed Hameed – Director | ESCALATION | Marine Site | Current staff to be replaced. Direct losses >MVR 5M; business damage >MVR 12M due to barge unavailability from staff failures. Cannot retain negligent staff. | — | DECISION – In progress | Confirm staff replacement timeline; identify root cause failures
78 | (Undated ~Mar) | 12:14 | AH Group R&M | Mohamed Hameed – Director | RECRUITMENT | Marine Site | Need to find a mechanic experienced in BOTH mechanical AND electrical. | — | OPEN – Recruitment required | Source dual-skilled mechanic
79 | (Undated ~Mar) | 12:16 | AH Group R&M | Mohamed Hameed – Director | MANAGEMENT | Marine Site | Will observe team cooperation following personnel changes before determining actual problem and taking further action. | — | MONITORING

## MATERIAL REQUESTS
SITE MATERIAL REQUESTS – Informal (WhatsApp) – No Purchase Order Number
# | Date Raised | Raised By | Site/Area | Item Description | Qty | UoM | Priority | Date Dispatched | Transport | Date Received | Status
1 | 26-Jan-26 | Sampath | BF | Perspex sheet | 1 | Nos | URGENT | 31-Jan-26 | Atoll Cute Crown | 31-Jan-26 | RECEIVED
2 | 26-Jan-26 | Sampath | BF | Silicone | 2 | Nos | URGENT | 31-Jan-26 | Atoll Cute Crown | 31-Jan-26 | RECEIVED
3 | 26-Jan-26 | Sampath | BF | Silicone gun | 1 | Nos | URGENT | 31-Jan-26 | Atoll Cute Crown | 31-Jan-26 | RECEIVED
4 | 26-Jan-26 | Sampath | BF | Large D-shackle for bucket hook | 1 | Nos | URGENT | — | — | — | OPEN – available Thilafushi; dispatch unconfirmed
5 | 26-Jan-26 | Sampath | BF | Diesel pump | 1 | Nos | URGENT | ~06-Feb-26 | — | 06-Feb-26 | RECEIVED (as Fuel pump)
6 | 26-Jan-26 | Sampath | BF | Grease gun | 1 | Nos | URGENT | 06-Feb-26 | — | 06-Feb-26 | RECEIVED
7 | 26-Jan-26 | Sampath | BF | Grease | — | — | NORMAL | — | — | — | UNKNOWN – available Thilafushi
8 | 26-Jan-26 | Sampath | BF | O-ring box | 1 | Nos | NORMAL | 31-Jan-26 | — | 31-Jan-26 | RECEIVED
9 | 26-Jan-26 | Sampath | BF | Radiator coolant | — | — | NORMAL | — | — | — | UNKNOWN – available Thilafushi
10 | 26-Jan-26 | Sampath | BF | Bucket teeth and pins | — | — | NORMAL | — | — | — | OPEN – not dispatched; 1 tooth removed 1 Mar
11 | 12-Feb-26 | Sampath | MF | Diesel filling hose for manual pump (20 ft) | 20 | Feet | NORMAL | — | — | — | OPEN
12 | 12-Feb-26 | Sampath | MF | Grease gun | 1 | Nos | NORMAL | — | — | — | OPEN
13 | 12-Feb-26 | Sampath | MF | Grease | — | — | NORMAL | — | — | — | OPEN
14 | 12-Feb-26 | Sampath | MF | Grease nipple for Komatsu 350 | — | — | NORMAL | — | — | — | OPEN
15 | 12-Feb-26 | Sampath | MF | Solenoid for Komatsu 350 | 1 | Nos | URGENT | 02-Mar-26 | Multiple | 02-Mar-26 | RECEIVED – WRONG FIT; correct OEM part still needed
16 | ~19-Feb-26 | Sampath | BF | Hydraulic oil (Komatsu) | 1 | Barrel | URGENT | — | — | 24-Feb-26 | RECEIVED – 209L barrel opened; only 50-60L found on check
17 | ~19-Feb-26 | Sampath | BF | Diesel filter (Komatsu) | — | — | URGENT | — | — | — | OPEN
18 | ~19-Feb-26 | Sampath | BF | Oil filter (Komatsu) | — | — | URGENT | 03-Mar-26 | Atoll Cute Crown | 03-Mar-26 | RECEIVED (fuel filter; oil filter not available at Goidhoo)
19 | ~19-Feb-26 | Sampath | BF | Solenoid (Komatsu 350) | 1 | Nos | URGENT | 02-Mar-26 | — | 02-Mar-26 | RECEIVED – WRONG PART; correct part still open
20 | ~19-Feb-26 | Sampath | BF | Grease | — | — | NORMAL | — | — | — | OPEN
21 | ~19-Feb-26 | Sampath | BF | Grease gun | 1 | Nos | NORMAL | — | — | — | OPEN
22 | ~19-Feb-26 | Sampath | BF/MF | Cotton waste | — | — | NORMAL | — | — | — | UNKNOWN
23 | ~19-Feb-26 | Sampath | BF – Dump Truck | Brake oil | — | — | NORMAL | — | — | — | OPEN
24 | ~19-Feb-26 | Sampath | BF – Dump Truck | All service filters | — | — | NORMAL | — | — | — | OPEN
25 | 20-Feb-26 | Sampath | BF | Adblue | — | — | NORMAL | 02-Mar-26 | — | 02-Mar-26 | RECEIVED (4 cans)
26 | 25-Feb-26 | Sampath | BF – Komatsu 350 | Correct solenoid + Allen screw size 4 ×2 | — | — | URGENT | — | — | — | OPEN – wrong part returned; OEM part number needed
27 | 28-Feb-26 | Sampath | BF – Kobelco 380 | Engine top cover (250×850mm) | 1 | Nos | URGENT | 01-Mar-26 | Launch | — | IN TRANSIT – in Malé for repair; confirmation pending
28 | 01-Mar-26 | Sampath | BF – Komatsu | Bucket tooth replacement | 1+ | Nos | NORMAL | — | — | — | OPEN
29 | 10-Feb-26 | Sampath | BF | Grease gun coupler (NPT 1/8 in.) | 1 | Nos | NORMAL | — | — | — | OPEN – no dispatch/receipt confirmed
30 | 07-Mar-26 | Sampath | BF – Komatsu | Hydraulic hose replacement | — | — | URGENT | — | — | — | IN PROGRESS – using available spare; replacement needed
31 | 15-Mar-26 | Sampath | BF – Kobelco | Jack seal for arm jack (hydraulic leak) | 1 | Nos | URGENT | — | — | — | OPEN – no dispatch confirmed
32 | 15-Mar-26 | Sampath | BF – PC50 | Oil & fuel filters for PC50 / Kubota 50 | — | — | HIGH | — | — | — | IN PROGRESS – photos sent 22 Mar; Janaka selecting
33 | ~Feb-26 | Sampath | BF – Dump Truck | Volvo A40D – all service items (oil viscosity high) | — | — | URGENT | — | — | — | OPEN – DO NOT OPERATE; service not confirmed

## PURCHASE REQUESTS
CONSOLIDATED PURCHASE REQUESTS – Antrac & Well Land (Janaka) + Site Informal Requests (Sampath)
# | Req No. | Date | Requested By | Entity | Category | Destination / Vessel | Item Description | Qty | UoM | Status | Notes
1 | antrac 2026/7 | 21-Feb-26 | Janaka | Antrac | Vessel Consumables | Antrac1 Dhoni | Water | 2000 | litres
2 | antrac 2026/7 | 21-Feb-26 | Janaka | Antrac | Vessel Consumables | Antrac1 Dhoni | Diesel | 1900 | litres
3 | antrac 2026/8 | 23-Feb-26 | Janaka | Antrac | Vessel Consumables | Antrac1 Dhoni | Water | 1000 | litres
4 | antrac 2026/8 | 23-Feb-26 | Janaka | Antrac | Vessel Consumables | Antrac1 Dhoni | Diesel | 1400 | litres
5 | antrac 2026/9 | 01-Mar-26 | Janaka | Antrac | Parts & Filters | Antrac1 Dhoni | Fuel filter element 2020pm 30 micron | 4 | Nos
6 | antrac 2026/9 | 01-Mar-26 | Janaka | Antrac | Parts & Filters | Antrac1 Dhoni | Lube oil filter 126650-35350 | 4 | Nos
7 | antrac 2026/9 | 01-Mar-26 | Janaka | Antrac | Parts & Filters | Antrac1 Dhoni | Greased gland packing 12mm | 1 | Nos
8 | wl-st-2026-4 | 19-Feb-26 | Janaka | Well Land | Site Consumables | Site 3 (BF/MF) | Water | 5 | tons
9 | wl-st-2026-5 | 22-Feb-26 | Janaka | Well Land | Site Consumables | Site 3 | Water | 5 | tons
10 | wl-st-2026-6 | 25-Feb-26 | Janaka | Well Land | Site Consumables | Site 3 | Water | 5 | tons
11 | wl-st-2026-7 | 28-Feb-26 | Janaka | Well Land | Site Consumables | Site 3 | Water | 5 | tons
12 | wl-st-2026-8 | 01-Mar-26 | Janaka | Well Land | Parts | Site 3 | Komatsu PC350 excavator bucket tooth | 4 | no's | Linked to site request; 1 tooth removed 1 Mar | Linked to site request; 1 tooth removed 1 Mar
13 | wl-lct-2027-6 | 26-Feb-26 | Janaka | Well Land | Vessel Consumables | LCT1 | Diesel (balance 1300L) | 3500 | litres
14 | wl-lct-2027-6 | 26-Feb-26 | Janaka | Well Land | Vessel Consumables | LCT1 | Water | 8 | tons
15 | wl-lct-2027-7 | 01-Mar-26 | Janaka | Well Land | Vessel Supplies | LCT1 | Canvas tarpaulin | 4 | no's
16 | 37-2026 | 11-Feb-26 | Janaka | Well Land | Lubricants | Site 3: vessels & workshop | 15W-40 engine oil | 1 | barrel
17 | 38-2026 | 14-Feb-26 | Janaka | Well Land | Provisions | Goidhoo project: staff | 1.5L drinking water | 20 | case
18 | 39-2026 | 15-Feb-26 | Janaka | Well Land | PPE | Site 3: welders | XL boiler suit (Robel – MPL) | 1 | kit
19 | 39-2026 | 15-Feb-26 | Janaka | Well Land | PPE | Site 3: welders | XL boiler suit (Nurul – W/L) | 1 | kit
20 | 40-2026 | 15-Feb-26 | Janaka | Well Land | Fuel | Goidhoo: machines & vehicles | Diesel | 2400 | litres
21 | 40-2026 | 15-Feb-26 | Janaka | Well Land | Lubricants | Goidhoo: machines & vehicles | Hydraulic oil | 40 | litres
22 | 41-2026 | 16-Feb-26 | Janaka | Well Land | Electrical | LCT1 | 15 AMP socket outlet | 1 | Nos
23 | 41-2026 | 16-Feb-26 | Janaka | Well Land | Electrical | LCT1 | Single sunk box | 1 | Nos
24 | 42-2026 | n/a | Janaka | Well Land | — | n/a | N/A (blank request) | — | — | Status '?' in original log – follow up with Janaka | Status '?' in original log – follow up with Janaka
25 | 43-2026 | 24-Feb-26 | Janaka | Well Land | Lubricants | Site 3 | SAE 68 hydraulic oil | 1 | barrel
26 | 44-2026 | 02-Mar-26 | Janaka | Well Land | Site Supplies | Site 3 | Fabric tarpaulin | 2 | Nos
27 | 44-2026 | 02-Mar-26 | Janaka | Well Land | PPE | Site 3 | Cotton gloves | 10 | bundles
28 | 44-2026 | 02-Mar-26 | Janaka | Well Land | Consumables | Site 3 | 4" paint refills | 3 | bundles
29 | 45-2026 | 02-Mar-26 | Janaka | Well Land | Fuel | Excavators and lorries | Diesel | 1200 | litres
30 | 46-2026 | 02-Mar-26 | Janaka | Well Land | Fuel | Bodufinolhu project | Diesel | 1000 | litres
31 | 47-2026 | 04-Mar-26 | Janaka | Well Land | PPE | Welders of MPL | XL boiler suit (Robel, welder) | 1 | Nos
32 | 47-2026 | 04-Mar-26 | Janaka | Well Land | PPE | Welders of MPL | XL boiler suit (Mokles, welder) | 1 | Nos
33 | 47-2026 | 04-Mar-26 | Janaka | Well Land | PPE | Welders of MPL | XL boiler suit (Rashid, welder) | 1 | Nos
34 | 47-2026 | 04-Mar-26 | Janaka | Well Land | PPE | Welders of MPL | Size 43 safety shoe (Nurul, welder) | 1 | Pair
35 | 48-2026 | 07-Mar-26 | Janaka | Well Land | Crew Supplies | Launch crew | Bed sheets | 2 | Nos
36 | 48-2026 | 07-Mar-26 | Janaka | Well Land | Crew Supplies | Launch crew | Pillows with covers | 2 | Nos
37 | 49-2026 | 07-Mar-26 | Janaka | Well Land | Provisions | Staff | Washing powder | 2 | case
38 | 50-2026 | 12-Mar-26 | Janaka | Well Land | Parts | Vehicles & PC70 excavator | 70Amp 12V battery (10"×7") | 2 | Nos
39 | 50-2026 | 12-Mar-26 | Janaka | Well Land | Parts | Vehicles & PC70 excavator | Battery terminals | 4 | Pair
40 | 50-2026 | 12-Mar-26 | Janaka | Well Land | PPE | Blasting helmet | 7"×5"×3mm clear glass (blasting helmet) | 12 | Nos
41 | 51-2026 | 18-Mar-26 | Janaka | Well Land | Parts | Komatsu PC350 high bed excav. | 12mm rubber hose (diesel hose) | 20 | Feet
42 | 52-2026 | 19-Mar-26 | Janaka | Well Land | PPE | Safety shoe & boiler suit to drivers | M boiler suit (Sojib, new driver) | 1 | Nos
43 | 52-2026 | 19-Mar-26 | Janaka | Well Land | PPE | Safety shoe & boiler suit to drivers | Size 40 safety shoe (Sojib) | 1 | Pair
44 | 52-2026 | 19-Mar-26 | Janaka | Well Land | PPE | Safety shoe & boiler suit to drivers | Size 41 safety shoe (Moyna Mia, driver) | 1 | Pair
45 | 53-2026 | 21-Mar-26 | Janaka | Well Land | PPE | Marine engineer | Safety boot size 46 (Paulson, marine engineer) | 1 | Pair
46 | 53-2026 | 21-Mar-26 | Janaka | Well Land | PPE | Marine engineer | Boiler suit XXXXXL (Paulson, marine engineer) | 1 | Nos
47 | 54-2026 | (pending) | Janaka | Well Land | — | — | Not yet raised – request number reserved | — | —
48 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Perspex sheet | 1 | Nos | Jan 31 batch | Jan 31 batch
49 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Silicone | 2 | Nos | Jan 31 batch | Jan 31 batch
50 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Silicone gun | 1 | Nos | Jan 31 batch | Jan 31 batch
51 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Large D-shackle for bucket hook | 1 | Nos | Available Thilafushi; dispatch unconfirmed | Available Thilafushi; dispatch unconfirmed
52 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Diesel pump | 1 | Nos | Received 6 Feb as 'Fuel pump' | Received 6 Feb as 'Fuel pump'
53 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Grease gun | 1 | Nos | 6 Feb receipt | 6 Feb receipt
54 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Grease | — | — | Available Thilafushi | Available Thilafushi
55 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | O-ring box | 1 | Nos | Jan 31 batch | Jan 31 batch
56 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Radiator coolant | — | — | Available Thilafushi | Available Thilafushi
57 | N/A (Site) | 26-Jan-26 | Sampath | Well Land | Machine Parts | BF – machines | Bucket teeth and pins | — | — | Not dispatched | Not dispatched
58 | N/A (Site) | 12-Feb-26 | Sampath | Well Land | Machine Parts | MF – Komatsu 350 | Diesel filling hose for manual pump (20ft) | 20 | Feet
59 | N/A (Site) | 12-Feb-26 | Sampath | Well Land | Machine Parts | MF – Komatsu 350 | Solenoid for Komatsu 350 | 1 | Nos | Correct OEM part still needed | Correct OEM part still needed
60 | N/A (Site) | 17-Feb-26 | Sampath | Well Land | Fuel | MF – stock | Diesel | 1200 | litres | MF stock 1600L + 7 empty barrels | MF stock 1600L + 7 empty barrels
61 | N/A (Site) | 17-Feb-26 | Sampath | Well Land | Fuel | MF – stock | Petrol | 200 | litres
62 | N/A (Site) | 17-Feb-26 | Sampath | Well Land | Fuel | BF – machines | Diesel | 1000 | litres

## RECEIPTS
RECEIPTS – All Confirmed Goods Received
# | Date Received | Items Received | Qty / Detail | Received By | Transport / Source | Confirmed By | Notes / Alerts
1 | Dump truck brake hoses | 2 hoses | Sampath | Ferry from Malé | Mohamed Hameed | Hydraulic hose still pending at this point
2 | 6 filters, Manual pump, O-ring box, Small grease gun, 2x Silicone, Silicone gun, 2x Lifting belts | Multiple | Sampath | Multiple dispatches (Goidhoo/Malé) | Ahmed Ziyad Hassan | Main batch from Malé/Goidhoo
3 | Starting Motor, Hose, O-ring set (Dump Truck), Filters | Multiple | Sampath (BF) | Atoll Cute Crown speedboat | Ahmed Ziyad Hassan | O-ring set confirmed for Volvo dump truck
4 | Manual pump, Small grease gun, O-ring box | 3 items | Thilafushi store | Dispatched from BF site | Mr. Ibrahim (instruction) | Sent to Thilafushi
5 | Fuel pump, Grease gun, 2x AC machines, Washing machine, AC gas R410A, Hydraulic barrel | 6 items | Sampath | — | — | Multi-item delivery to BF
6 | Hydraulic barrel (209L) | 1 barrel | Sampath | — | — | ⚠️ ALERT: Barrel arrived opened; only 50-60L found on check. Usage log now mandatory.
7 | Hydraulic hose (drum truck) | 1 hose | Sampath (BF) | Moosabe vessel | Ahmed Ziyad Hassan | Sent by Ahmed; received at BF
8 | 3x Komatsu burst hoses sent to Thulhaadhoo for repair | 3 hoses (outbound) | Sampath | Atoll Cute King | Ahmed Ziyad Hassan | Hoses sent for repair
9 | Parts package – Komatsu solenoid + Kobelco gasket | 1 package | Sampath | Goidhoo ferry | Mohamed Hameed (identified) | ⚠️ Solenoid socket mismatch – wrong part returned
10 | Kobelco 10x filters (5 oil+5 fuel), Komatsu solenoid, 1 belt (Goidhoo), 4x Adblue cans | Multiple | Sampath | — | — | Correction: originally stated 13 filters; actual 10
11 | Komatsu fuel filter (from Goidhoo) | — | Site | Atoll Cute Crown | Mushthaq coordinate | Fuel filter only; oil filter not available at Goidhoo
12 | Eurofil oil & fuel filters batch | Multiple | Sampath | — | Mohamed (inventory) | Used for Kobelco and Komatsu servicing
13 | Osaka oil & fuel filter photos for PC50 (photos – not physical goods) | Photos | Ndirangu Nginga | On-site (phone camera) | Janaka (to select correct part) | Janaka to identify and order correct filters

## INCIDENTS & ISSUES
INCIDENTS & ISSUES – Machine Failures, Breakdowns, Damage, Stock Discrepancies
# | Date | Machine / Asset | Incident / Issue | Root Cause | Immediate Action | Resolution Status | Outstanding Action
1 | 26-Jan-26 | SK 235 Excavator | Starter motor failure – out of order | Motor failure | Sent to Malé for repair | UNKNOWN – no return confirmation
2 | 26-Jan-26 | Kobelco (High Bed) | Bucket pin repair pending materials | Materials unavailable | Boom pin done 26 Jan; bucket pin done 27 Jan | RESOLVED
3 | 26-Jan-26 | BF Dump Truck | Awaiting hose from Malé (sent 22 Jan) | Hose failure | Sent to Malé 22 Jan; returned via ferry 27 Jan | RESOLVED
4 | 26-Jan-26 | MF Dump Truck | Oil leakage identified | Unknown | Mechanic sent with Komatsu 29 Jan | PARTIALLY RESOLVED – final confirmation not on record
5 | 28-Jan-26 | Komatsu (High Bed) | Diesel air lock – air in fuel system | Diesel filter blockage | Mechanic informed; diesel filter required | OPEN – filter procured Mar; monitored
6 | 29-Jan-26 | BF Dump Truck | Brake hose burst at 14:45 during Evosun hire | Hose failure | Evosun mechanic assisted; repair done | RESOLVED
7 | 31-Jan-26 | Multiple BF machines | All machines except Kobelco broken – site at standstill | Multiple concurrent failures | Emergency parts dispatched from Malé/Goidhoo | RESOLVED by early Feb
8 | 04-Feb-26 | Kobelco (High Bed) | Steel bush cracks found during Malé repair | Rock boulder unloading impact | Temporary weld; cabin removal needed for permanent fix | PARTIAL – temporary fix; permanent deferred
9 | 13-Feb-26 | BF Dump Truck | Hydraulic hose burst | Hose wear/failure | Hose sent to Malé; returned via Moosabe 14 Feb | RESOLVED
10 | 15-Feb-26 | Komatsu (High Bed) | Small hole in steel fuel pipe | Wear/damage | Sent to Thuladhoo for gas welding | UNKNOWN – welding result not confirmed
11 | 15-Feb-26 | Unknown Excavator | Hydraulic hose burst | Hose failure | Spare dump truck hose used to fix | RESOLVED – dump truck spare consumed
12 | 19-Feb-26 | BF Dump Truck | Hydraulic hose damage – unsafe near sea | Hose deterioration | Sent to Malé; MF dump truck used as interim | IN PROGRESS – repair confirmation pending
13 | 19-Feb-26 | Komatsu (High Bed) | Machine issues (unspecified – video) | Unknown | Mechanic attended; Ndirangu: Fixed 12:15 | RESOLVED
14 | 21-Feb-26 | Kobelco (High Bed) | Water leaking through gasket – cannot operate | Gasket failure | Gasket ordered; mechanic arranged (23 Feb) | RESOLVED – Kobelco working by 03 Mar
15 | 22-Feb-26 | Komatsu (High Bed) | 3rd hose burst (cumulative) | Repeated hose failures | Hoses sent to Thulhaadhoo 23 Feb | RESOLVED after repair
16 | 24-Feb-26 | BF Dump Truck (Volvo A40D) | High oil viscosity – unsafe to operate | Service overdue | STOP ORDER issued by Mushthaq; checklist sent | OPEN – Immediate service required
17 | 24-Feb-26 | Stock / Inventory | Hydraulic oil 209L barrel: only 50-60L found on check | Barrel received already opened; unauthorized use | Mushthaq: no use without GM knowledge; usage log enforced | CONTROL ISSUE – log implemented
18 | 25-Feb-26 | Komatsu 350 | Wrong solenoid received (pilot block – socket mismatch) | Wrong part dispatched | Returned wrong part; sample to Malé for correct sourcing | OPEN – Correct OEM solenoid still needed
19 | 28-Feb-26 | Kobelco 380 | Engine top cover cracked (250×850mm) | Deterioration/impact damage | Sent to Malé for repair 28 Feb / 1 Mar | IN PROGRESS – confirmation pending
20 | 01-Mar-26 | Komatsu (High Bed) | Bucket tooth removed/lost | Impact/wear | Replacement requested | OPEN
21 | 07-Mar-26 | Komatsu (High Bed) | Hydraulic hose burst (4th event) | Recurring failure | Using available spare; Kobelco covering | IN PROGRESS – send for replacement
22 | 15-Mar-26 | Kobelco (High Bed) | Hydraulic leak in arm jack – needs jack seal | Seal failure | Jack seal requested @Mushthaq 15 Mar | OPEN – Jack seal not yet dispatched
23 | ~Mar-26 | AH Group Barges | Staff negligence resulting in barge unavailability – direct loss >MVR 5M; business damage >MVR 12M | Staff failures | Marine mechanic deployed under Dhanushka; staff replacement decision | IN PROGRESS – monitoring new team

## OPEN ITEMS
OPEN ITEMS – FOLLOW-UP TRACKER ¦ Review Daily
# | Date Raised | Source Group | Category | Open Item / Action Required | Responsible | Priority | Target | Status
1 | 26-Jan-26 | BF Machine & Diesel | MATERIAL | Large D-shackle for bucket hook – available Thilafushi; dispatch to BF not confirmed | Janaka / Ahmed Ziyad | URGENT | — | OPEN
2 | 26-Jan-26 | BF Machine & Diesel | MATERIAL | Bucket teeth and pins – not dispatched; 1 tooth removed 1 Mar | Janaka / Ahmed Ziyad | HIGH | — | OPEN
3 | 26-Jan-26 | BF Machine & Diesel | MAINTENANCE | SK 235 starter motor – sent to Malé; repair/return not confirmed | Ahmed Ziyad / Janaka | HIGH | — | UNKNOWN
4 | 12-Feb-26 | BF Machine & Diesel | MATERIAL | MF – Diesel filling hose for manual pump (20ft) | Janaka | MEDIUM | — | OPEN
5 | 12-Feb-26 | BF Machine & Diesel | MATERIAL | MF – Grease and Grease nipple for Komatsu 350 | Janaka | MEDIUM | — | OPEN
6 | 15-Feb-26 | BF Machine & Diesel | MAINTENANCE | Komatsu fuel pipe sent to Thuladhoo for welding – result not confirmed | Sampath / Ndirangu | HIGH | — | UNKNOWN
7 | ~24-Feb-26 | BF Machine & Diesel | MAINTENANCE | BF Dump Truck – DO NOT OPERATE. High oil viscosity. Immediate full service required. Volvo A40D checklist to be completed and returned. | Mushthaq / Janaka / Mechanic | URGENT | ASAP | OPEN
8 | ~24-Feb-26 | BF Machine & Diesel | MATERIAL | BF Dump Truck – Brake oil + all service filters | Janaka | HIGH | — | OPEN
9 | 24-Feb-26 | BF Machine & Diesel | ADMIN | Volvo A40D maintenance checklist to be completed by Sampath and returned to Mushthaq | Sampath | HIGH | ASAP | PENDING
10 | 24-Feb-26 | BF Machine & Diesel | ADMIN / CONTROL | Stock usage log mandatory – all consumables (oil, hydraulic fluid) must be recorded; no use without GM approval | Sampath / Ndirangu | URGENT | IMMEDIATE | CONTROL REQUIRED
11 | 25-Feb-26 | BF Machine & Diesel | MAINTENANCE | Correct Komatsu 350 solenoid – wrong part received twice; need OEM serial/part number; sample sent to Malé | Janaka / Ahmed Ziyad | URGENT | ASAP | OPEN
12 | 28-Feb-26 | BF Machine & Diesel | MAINTENANCE | Engine top cover (Kobelco 380) in Malé for repair – confirmation pending | Ahmed Ziyad / Mechanic | URGENT | ASAP | IN PROGRESS
13 | 01-Mar-26 | BF Machine & Diesel | MATERIAL | Komatsu bucket tooth replacement | Janaka | MEDIUM | — | OPEN
14 | 07-Mar-26 | BF Machine & Diesel | MAINTENANCE | Komatsu hose (burst 7 Mar) – proper replacement needed; currently on available spare | Janaka / Ahmed Ziyad | HIGH | — | IN PROGRESS
15 | 10-Feb-26 | BF Machine & Diesel | MATERIAL | Grease gun coupler (NPT 1/8 in.) – no receipt confirmation | Janaka / Ahmed Ziyad | MEDIUM | — | UNKNOWN
16 | 15-Mar-26 | BF Machine & Diesel | MATERIAL | Jack seal for Kobelco arm jack (hydraulic leak) | Mushthaq / Janaka | URGENT | ASAP | OPEN
17 | 15-Mar-26 | BF Machine & Diesel | MATERIAL | Oil & fuel filters for PC50 / Kubota 50 small excavator | Janaka | HIGH | — | IN PROGRESS – photos sent 22 Mar
18 | 15-Mar-26 | BF Machine & Diesel | OPERATIONS | LCT + 2 excavators (high bed + low bed) + truck to be transferred to MF before monsoon | Sampath / AH | HIGH | ASAP | ARRANGED – confirm LCT arrival
19 | 22-Mar-26 | BF Machine & Diesel | MAINTENANCE | PC50 filter photos sent to Janaka – select and order correct parts | Janaka | HIGH | 23-Mar-26 | IN PROGRESS
20 | 22-Mar-26 | BF Machine & Diesel | OPERATIONS | Nasru to load items from Maniyafaru tomorrow morning | Sampath / AH | MEDIUM | 23-Mar-26 | PENDING
21 | 22-Mar-26 | BF Machine & Diesel | OPERATIONS | Komatsu low bed to MF for rock boulder work (low tide window) | Sampath / AH | HIGH | ASAP | ORGANIZING
22 | — | BF Machine & Diesel | MAINTENANCE | MF Dump Truck oil leakage – final fix confirmation not on record | Mechanic / Sampath | HIGH | — | UNKNOWN
23 | — | BF Machine & Diesel | MAINTENANCE | Kobelco steel bush cracks – permanent repair (cabin removal) deferred | Mechanic / Janaka | MEDIUM | — | DEFERRED
24 | ~24-Feb-26 | WL Logistic Group | OPERATIONS | TUG 1 Repair & Maintenance – who is responsible? Redirected to Ziyadh. Confirm Ziyadh contacted and R&M plan in place. | Mushthaq / Ziyadh | HIGH | — | OPEN
25 | ~24-Feb-26 | WL Logistic Group | BUSINESS DEV | Food supply proposal – follow up on outcome of client discussion | Nashwan / Mohamed Hameed | LOW | — | OPEN
26 | ~24-Feb-26 | WL Logistic Group | VESSEL OPS | Dhidhoo food delivery – confirm completed | Nashwan | MEDIUM | — | UNKNOWN
27 | ~Mar-26 | AH Group R&M | RECRUITMENT | Find dual-skilled mechanic (mechanical + electrical) for marine site | Mohamed Hameed / Dhanushka | HIGH | — | OPEN
28 | ~Mar-26 | AH Group R&M | MAINTENANCE | Staff replacement at marine site – confirm new team deployed under Dhanushka | Dhanushka | HIGH | — | IN PROGRESS
29 | Various | All | MATERIAL | Adblue stock – confirm sufficient quantity at BF after 4 cans received 2 Mar | Sampath / Janaka | MEDIUM | — | UNKNOWN
30 | Various | All | FUEL | Diesel delivery confirmation – 4000L to BF+MF via 6 barrels from Thulhaadhoo | Sampath / AH | HIGH | — | UNKNOWN
31 | 42-2026 | Purchase Requests | PROCUREMENT | Request 42-2026 – status '?' in log. Clarify with Janaka what this request was and its status. | Janaka / Mushthaq | MEDIUM | — | UNKNOWN
32 | 54-2026 | Purchase Requests | PROCUREMENT | Request 54-2026 – number reserved but items not yet raised. Follow up with Janaka. | Janaka | LOW | — | PENDING

## DIRECTED AT MUSHTHAQ
⭐ DIRECTED AT MUSHTHAQ (Ali Mushthaq Ibrahim – GM Logistics) ¦ Personal Action Register ¦ All Groups
This is YOUR dashboard. Every message/request directed at you from all groups is logged here. Fill in 'Your Action / Response' and update STATUS after each action. Sources: BF Machine & Diesel Ops ¦ WL Logistic Group ¦ AH Group R&M
# | Date | Time | Source Group | Sent By / Role | Request / Message Directed at You | Action Required | Your Action / Response | Status | Priority | Date Actioned
1 | 09-Feb-26 | 11:54 | BF Machine & Diesel | Mohamed Hameed – Director | @Mushthaq (Well Land) – Ndirangu hasn't gotten help with jetty booking. Situation? | Advise on Ndirangu's travel arrangement to BF | Jackson sent to ferry; reaching 12pm ferry (11:55 confirmed) | CLOSED | MEDIUM | 09-Feb-26
2 | 19-Feb-26 | 07:58 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Good morning. Materials required: Komatsu: Hydraulic oil, Diesel filter, Oil filter, Solenoid, Grease, Grease gun, Cotton waste (both sites). BF Dump Truck: Brake oil + all service filters. Some ordered per Janaka – ETA? | 1. Confirm ETA on ordered items from Janaka. 2. Source: brake oil, cotton waste, grease gun (MF). 3. Coordinate Janaka. | — | OPEN | HIGH
3 | 20-Feb-26 | 06:45 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) @Janaka – Can you send Adblue please? | Arrange Adblue dispatch to BF | 4 Adblue cans delivered to BF on 02-Mar-26 | CLOSED | MEDIUM | 02-Mar-26
4 | 21-Feb-26 | 17:46 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Kobelco cannot operate. Mechanic: water leaking through gasket. | Arrange gasket + mechanic urgently for Kobelco | Monitored; gasket sourced; Kobelco fixed by 03-Mar-26 | CLOSED | HIGH | 03-Mar-26
5 | 22-Feb-26 | 16:05 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Another hose burst on Komatsu. Sending via Thuladhoo/Musa to Malé tomorrow. Total 3 hoses burst; 2 already in Malé. | Confirm hose repair arrangement. Ensure all 3 hoses repaired/replaced. | Hoses sent via Atoll Cute King 23-Feb to Thulhaadhoo for repair | CLOSED | HIGH | 23-Feb-26
6 | 24-Feb-26 | 15:04 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Dump truck operator: oil viscosity high, needs immediate service. Safe to operate? | 1. Issue stop order immediately. 2. Arrange full service. 3. Send Volvo A40D checklist for inspection. | Responded: IT IS NOT SAFE. DO NOT OPERATE. Sent Volvo A40D checklist PDF to Sampath. | OPEN – SERVICE NOT YET CONFIRMED | URGENT | 24-Feb-26
7 | 24-Feb-26 | 15:05 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Please send me the costing for the repair works (dump truck). | Clarify that repair costing is not your responsibility. Confirm mechanic assessment. | Responded: Not my role to cost repairs. Has mechanic checked? Sampath: No idea – will check. | OPEN – Awaiting mechanic assessment | URGENT | 24-Feb-26
8 | 24-Feb-26 | 15:33 | BF Machine & Diesel | Mushthaq [self-initiated] | Sent Volvo A40D Immediate Troubleshooting Checklist PDF to Sampath for truck inspection. | Receive completed checklist back from Sampath and file. | — | PENDING – Checklist not returned | HIGH
9 | 24-Feb-26 | 16:21 | BF Machine & Diesel | Mushthaq [self-initiated] | Discovered hydraulic oil barrel: 209L received but only 50-60L remaining on check. Barrel arrived opened. | 1. Enforce usage log with immediate effect. 2. Investigate who used ~150L without authorization. 3. Implement: nothing used without GM knowledge. | Informed Sampath: nobody uses anything without informing me. Sampath: Ok. | CONTROL ISSUE – Monitor | URGENT | 24-Feb-26
10 | 25-Feb-26 | 10:30 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq + @Janaka – Solenoid received does not match (wrong part – pilot block). Need correct solenoid + Allen screw size 4 ×2 for Komatsu 350 top of hydraulic pump. | 1. Arrange correct solenoid sourcing (get OEM serial/part number from mechanic). 2. Return wrong part. 3. Janaka to check other parts shops. | Noted; Pilot block returned. Janaka checking. | OPEN – Correct solenoid needed | URGENT
11 | 28-Feb-26 | 12:26 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Rock boulder shipment arriving 4 March. Two excavators must be fixed immediately. | Ensure both excavators (Komatsu + Kobelco) operational before 4 March. Escalate parts if needed. | Responded: I am following this. Kobelco back 3 Mar; Komatsu back 4 Mar. | CLOSED | URGENT | 04-Mar-26
12 | 28-Feb-26 | 16:42 | BF Machine & Diesel | Mohamed Hameed – Director | @Mushthaq (Well Land) – Really we need to do your responsibility properly. If anyone told this before it went to this level I am able to do myself. I need to know what is happening. Those who cannot take responsibility I urge to resign. | 1. Improve real-time information flow from site. 2. Ensure Sampath/Ndirangu report proactively. 3. Acknowledge accountability. | Responded: I need to know what is happening; only then can I attend. I am looking into this. | ACTIONED – Ongoing oversight | HIGH | 28-Feb-26
13 | 01-Mar-26 | 11:30 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) @Ahmed Ziyad Hassan – Is it possible to send engine cover tomorrow? | Confirm Ahmed Ziyad can dispatch engine cover (Kobelco 380, 250×850mm) to Thulhaadhoo tomorrow. | Ahmed: Yes, sure (confirmed 01-Mar). | ARRANGED | MEDIUM | 01-Mar-26
14 | 03-Mar-26 | 08:45 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Komatsu cannot work. Needs oil + diesel filter. No Komatsu filters on site. Goidhoo has fuel filter only. Can you coordinate with Goidhoo and send fuel filter today? | Coordinate with Goidhoo to send Komatsu fuel filter on today's ferry. | Responded: Okay. Coordination done. Fuel filter dispatched via Atoll Cute Crown. Oil filter still needed. | PARTIALLY CLOSED – Oil filter still open | HIGH | 03-Mar-26
15 | 15-Mar-26 | 07:53 | BF Machine & Diesel | Sampath – Project Manager | @Mushthaq (Well Land) – Hydraulic leak in Kobelco arm jack. Need: 1) Jack seal 2) Hydraulic 20L (site: 20L) 3) Engine oil 65L (site: 65L) 4) Coolant 10L (site: 10L) 5) Adblue 40L (site: 40L) 6) Oil+Fuel filters PC50. | 1. Source and dispatch jack seal for Kobelco arm URGENTLY. 2. Arrange PC50 filters (Janaka to identify from photos). 3. Check if site stock levels sufficient for fluids. | Responded: Yes. We are on it. (17-Mar-26) | IN PROGRESS – Jack seal + PC50 filters pending dispatch | URGENT
16 | ~24-Feb-26 | ~17:07 | WL Logistic Group | Nashwan – Antrac Ops | Who is looking after TUG 1 repair and maintenance? (no answer; Hannan said: call Ziyadh) | Clarify TUG 1 R&M responsibility and ownership. Contact Ziyadh. Establish formal R&M schedule for TUG 1. | — | OPEN | HIGH
17 | ~24-Feb-26 | ~10:49 | WL Logistic Group | Mohamed Hameed – Director | Maybe you can propose food supply also to [the food logistics client]. | Evaluate food supply opportunity; respond to Mohamed Hameed with position. | — | OPEN | LOW