## Antrac
# | Date | Request no. | Qty | Uom | Description | Requested to: | Requested by |  | Status
1 | 2026-02-21 | antrac 2026/7 | 2000 | litres | water | Antrac1 Dhoni | Antrac | Janaka
|  |  | 1900 | litres | diesel | Antrac1 Dhoni | Antrac | Janaka
2 | 2026-02-23 | antrac 2026/8 | 1000 | litres | water | Antrac1 Dhoni | Antrac | Janaka
|  |  | 1400 | litres | diesel | Antrac1 Dhoni | Antrac | Janaka
3 | 2026-03-01 | antrac 2026/9 | 4 | Nos | 2020 pm, 30 micron fuel filter element | Antrac1 Dhoni | Antrac | Janaka
|  |  | 4 | Nos | 126650-35350 lube oil filter | Antrac1 Dhoni | Antrac | Janaka
|  |  | 1 | Nos | 12mm greased gland packing | Antrac1 Dhoni | Antrac | Janaka
4
5
6

## WellLand
# | Date | Request no. | Qty | Uom | Description | Requested to: | Requested by |  | Status
1 | 2026-02-19 | wl-st-2026-4 | 5 | tons | water | site3 | Welland | Janaka
2 | 2026-02-22 | wl-st-2026-5 | 5 | tons | water | site3 | Welland | Janaka
3 | 2026-02-25 | wl-st-2026-6 | 5 | tons | water | site3 | Welland | Janaka
4 | 2026-02-28 | wl-st-2026-7 | 5 | tons | water | site3 | Welland | Janaka
5 | 2026-03-01 | wl-st-2026-8 | 4 | no's | komatsu pc 350 excavator's bucket tooth | site3 | Welland | Janaka
6
7
# | Date | Request no. | Qty | Uom | Description | Requested to: | Requested by |  | Status
1 | 2026-02-26 | wl-lct-2027-6 | 3500 | litres | diesel (balance 1300 litres) | LCT1 | Welland | Janaka
|  |  | 8 | tons | water | LCT1 | Welland | Janaka
3 | 2026-03-01 | wl-lct-2027-7 | 4 | no's | canvas tarpaulin | LCT1 | Welland | Janaka
4
5
6
# | Date | Request no. | Qty | Uom | Description | Requested to: | Requested by |  | Status
1 | 2026-02-11 | 37-2026 | 1 | barrel | 15w-40 engine oil | site3: vessels & workshop | Welland | Janaka
2 | 2026-02-14 | 38-2026 | 20 | case | 1.5 liters drinking water | goidhoo project: staff | Welland | Janaka
3 | 2026-02-15 | 39-2026 | 1 | kit | Xl size boiler suit (robel-mpl) | site3: welders | Welland | Janaka
|  |  | 1 | kit | xl size boiler suit(nurul) w/l |  | Welland | Janaka
4 | 2026-02-15 | 40-2026 | 2400 | litres | diesel | goidhoo project: machines & vehicles | Welland | Janaka
|  |  | 40 | litres | hydaulic oil |  | Welland | Janaka
5 | 2026-02-16 | 41-2026 | 1 | Nos | 15 AMP socket outlet | LCT1 | Welland | Janaka
|  |  | 1 | Nos | single sunk box |  | Welland | Janaka
6 | n/a | 42-2026 | n/a | n/a | n/a | n/a |  |  | ?
7 | 2026-02-24 | 43-2026 | 1 | barrel | sae 68 hydraulic oil | site3: | Welland | Janaka
8 | 2026-03-02 | 44-2026 | 2 | Nos | fabric tarpaulin | site3: | Welland | Janaka
|  |  | 10 | Budles | cotton gloves |  | Welland | Janaka
|  |  | 3 | Budles | 4" refills |  | Welland | Janaka
9 | 2026-03-02 | 45-2026 | 1200 | litres | diesel | excavators and lorries | Welland | Janaka
| 2026-03-02 | 46-2026 | 1000 | litres | diesel | Bodufinolhu project
| 2026-03-04 | 47-2026 | 1 | Nos | Size xl boiler suit Robel (welder) | welders of MPL
|  |  | 1 | Nos | Size xl boiler suit mokles (welder)
|  |  | 1 | Nos | Size xl boiler suit rashid (welder)
|  |  | 1 | Pair | Size 43 safety shoe nurul (welder)
| 2026-03-07 | 48-2026 | 2 | Nos | Bed sheets | Launch Crew
|  |  | 2 | Nos | Pillows with covers
| 2026-03-07 | 49-2026 | 2 | Case | Washing Powder | Staff
| 2026-03-12 | 50-2026 | 2 | Nos | 70 ampx12v battery (10”x7”) | vehicles and pc 70 excavator
|  |  | 4 | Pair | Battery terminal
|  |  | 12 | Nos | 7”x 5” x 3mm clear glass ( for blasting helmet)
| 2026-03-18 | 51-2026 | 20 | Feet | 12mm rubber hose ( diesel hose) | komatsu pc 350 high bed excavator
| 2026-03-19 | 52-2026 | 1 | Nos | Size m boiler suit (sojib, new driver) | safety shoe and boiler suit to drivers
|  |  | 1 | Pair | Size 40 safety shoe (sojib, new driver)
|  |  | 1 | Pair | Size 41 safety shoe (moyna mia, driver)
| 2026-03-21 | 53-2026 | 1 | Pair | Saety Boot size 46 (Paulson, marine engineer)
|  |  | 1 | Nos | Boiler suit XXXXXL (Paulson, marine engineer)
54-2026

## Project sites
Material requests
# | Date | Request no. | Qty | Uom | Description | Requested to: | Requested by | Status
| 2026-01-26 | N/A | 1 | Nos | 1. Perspex sheet (Urgent) | The following materials are required for machine operations. Items marked as urgent are needed immediately:
|  |  | 2 | Nos | 2. Silicone (Urgent)
|  |  | 1 | Nos | 3. Silicone gun (Urgent)
|  |  | 1 | Nos | 4. Large D-shackle for bucket hook (Urgent)
|  |  | 1 | Nos | 5. Diesel pump (Urgent)
|  |  | 1 | Nos | 6. Grease gun (Urgent)
7. Grease
8. O-ring ox
9. Radiator coolant
10. Bucket teeth and pins
| 2026-02-12 | N/A | 20 | Feet | 1. Diesel filling hose for manual pump (20 ft) | Below items require for Muthaafushi,
2. Grease gun
3. Grese
4. Grease nipple for Komatsu 350
5. Solenoid for Komatsu 350
| 2026-02-17 | N/A |  |  | 1. Hydraulic oil | For machinery, Komatsu
2. Diesel filter
3. Oil filter
4. Solenoid
5. Grease
6. Grease gun
7. Cotton waste for both sites
| 2026-02-17 | N/A |  |  | 1. Break oil | BF drump truck
2. All the required filters for service.
| 2026-02-17 | N/A | 1200 |  | 1. Diesel | Muthaafushi stok is 1600 Diesel. And they have 7 empty barrels.
|  |  | 200 |  | 2. Petrol
|  |  | 1000 |  | 1. Diesel | Then please send to Bodufiolhu
Materials received notification from Sites
| 2026-01-31 |  |  |  | Received, 1. 6 filters 2. Manual pump 3. O ring box 4. Small grease gun 5. 2 silicone 6. Silicone gun 7. 2 lifting belts
| 2026-02-06 |  |  |  | Received, 1. Fuel pump 2. Grease gun 3. Two AC machines 4. Washing machine 5. AC gas R410A 6. Hydraulic barrel

## Machine Status
2026-01-26 | *Machine Status* Bodufinolhu • Komatsu (High Bed) – Currently engaged in coconut tree planting. Will be moved to Muthaafushi after the Kobelco excavator arm and bucket repairs are completed. However, machine movement is currently slow. • Kobelco (High Bed) – Boom pin repair will be completed today. Bucket pin repair is pending, awaiting materials. • SK 235 – Out of order. Starter motor will be sent to Malé by tomorrow. • PC50 (Small Excavator) – Engaged in coconut tree planting. • Dump Truck – Awaiting hose replacement (sent to Malé on the 22nd). Muthaafushi • Dump Truck – Oil leakage identified. A mechanic will be sent after repairs for both the Komatsu and the dump truck.
2026-01-27 | *Machine Status* Bodufinolhu • Komatsu (High Bed) – Currently engaged in coconut tree planting. Will be moved to Muthaafushi after repairing slow movement. • Kobelco (High Bed) – Boom pin and Bucket pin repaired. Engaged to coconut planting • SK 235 – Out of order. Starter motor sent to Malé today. • PC50 (Small Excavator) – Engaged in coconut tree planting. • Dump Truck – Awaiting hose replacement (sent to Malé on the 22nd). Muthaafushi • Dump Truck – Oil leakage identified. A mechanic will be sent after repairs for both the Komatsu and the dump truck.
2026-01-28 | *Machine Status* Bodufinolhu • Komatsu (High Bed) – Currently engaged in coconut tree planting. Will be moved to Muthaafushi when LCT is available. But still there are some issues with Diesel supply (Air lock). Mechanic informed that the diesel filter required to sort it out. • Kobelco (High Bed) – Hired to Evosun • SK 235 – Out of order. Starter motor sent to Malé yesterday. • PC50 (Small Excavator) – Engaged in coconut tree planting. • Dump Truck – Hired to Evosun Muthaafushi • Dump Truck – Oil leakage identified. A mechanic will be sent with Komatsu.
2026-01-29 | *Machine Status* Bodufinolhu • Komatsu (High Bed) – Engaged in coconut tree planting till 14.00 Hrs. Then sent to Muthafushi with Mechanic. • Kobelco (High Bed) – Hired to Evosun till 14.00 Hrs. Then engage to coconut tree planting. • SK 235 – Out of order. Starter motor sent to Malé yesterday. • PC50 (Small Excavator) – Engaged in coconut tree planting. • Dump Truck – Hired to Evosun. *14.45 Hrs break hose burst*. Planning to repair. Evosun mechanic will help on this. Muthaafushi • Dump Truck – Oil leakage identified. A mechanic went with Komatsu.