## 📊 Dashboard
ANTRAC HOLDING GROUP ¦ WELL LAND INVESTMENT PVT. LTD. ¦ OPERATIONS REGISTER
Well Land Ops Command Center — Fleet · Marine · Staff · Procurement · Rentals · Compliance
🚛 HEAVY FLEET (20 vehicles total — 4 new excavators added)
Total Fleet |  |  | At Thilafushi |  |  | At Project Sites |  |  | Location Unknown | Rental Eligible
20 |  |  | 5 |  |  | 2 |  |  | 11 | 0
inc. 4 new |  |  | Currently DOWN |  |  | No rental |  |  | Verify urgently | Thilafushi DOWN
⚓ MARINE FLEET (4 vessels)
LCT 1 |  |  | Dhoni 1 |  |  | Speed Boat 1 |  |  | Speed Boat 2 | Permits Tracked
Active |  |  | Active |  |  | Running |  |  | Drydocked | 0
In service |  |  | Ferry/supply |  |  | Fast transport |  |  | ⚠ Verify identity | ⚠ Fill dates now
👥 STAFF (31 engaged — expand as needed)
Total Engaged |  |  | Full Time |  |  | Probation |  |  | Marine | Land / Terminal
31 |  |  | 23 |  |  | 7 |  |  | 12 | 18
All categories |  |  | Active |  |  | incl. Ops/GM |  |  | Captains + crew | Ops + drivers
🔴 OPEN ACTIONS (fill manually — update daily)
# | Type | Ref | Subject / Asset | Raised By | Site | Urgency | Due | Status | Notes
1 | PR — CRITICAL | WL-PR-0001 | WL-HV-0002 VOLVO A40G — hydraulic hose leaking (Muthaafushi) | Janaka | Muthaafushi | CRITICAL |  | Open | Obtain quotes — unresolved since 15 Mar 2026.
2 | PR — CRITICAL | WL-PR-0006 | WL-HV-0006 KOMATSU PC350 — engine oil hose burst (Muthaafushi) | Sampath | Muthaafushi | CRITICAL | 22/04/2026 | In Progress | Fabrication done. Dispatching 22 Apr ferry → Thulhaadhoo → Idrees.
3 | DECISION REQ | WL-PR-0010 | WL-HV-0007 hydraulic pump — awaiting Hameed approval. USD 6,000 recon pump. | Mushthaq | Bodufinolhu | CRITICAL | ASAP | Pending | Engineer MVR 800/day accruing from 13 Apr. Every day of delay = cost.
4 | PAYMENT | WL-PR-0004 | Solenoid valve (×1) held by Venkata at site — payment outstanding (MVR 7,992 set) | Mushthaq | Bodufinolhu | URGENT | ASAP | Open | Release payment to unblock WL-HV-0007 repair.
5 | PARTS DISPATCH | WL-PR-0005 | Hydraulic adapter — fabricated, dispatching 22 Apr ferry → Thulhaadhoo → Idrees | Mushthaq | Bodufinolhu | URGENT | 22/04/2026 | In Progress | Confirm delivery with Sampath after ferry.
6 | CONFIRM DEL | WL-PR-0007/008 | Hydraulic filters (main + strainer) — dispatched to Muthaafushi. Confirm receipt. | Mushthaq | Muthaafushi | URGENT |  | Open | Confirm with Janaka / Sampath.
7 | CONFIRM DEL | WL-PR-0009 | Arm & boom seal kits — dispatched ~15 Apr to Bodufinolhu. Confirm receipt. | Mushthaq | Bodufinolhu | URGENT |  | Open | Confirm installation status with Sampath.
8 | VERIFY | WL-HV-0009 | WL-HV-0009 KOMATSU PC350 — location and status unknown | Mushthaq | Unknown | URGENT |  | Open | Confirm with Sampath / Janaka urgently.
9 | VERIFY | WL-MV-0004 | Speed Boat 2 — drydocked — same asset as SB1? |  |  | URGENT |  | Open | Confirm with Janaka.
10 | ENGINEER COST | IEPL-Venkata | Mr. Venkata engineer charges MVR 800/day from 13 Apr — accruing daily | Mushthaq | Bodufinolhu | URGENT |  | Open | Linked to pump decision. Resolve with Hameed.
11 | DOCS | WL-HV-0017~0024 | New units — complete chassis, engine, insurance, registration docs |  | Thilafushi/Bodufinolhu | HIGH |  | Partial | Partial data in Fleet sheet. Obtain full docs for all new units.
12 | WORK PERMIT | WL-EMP-0031 | Dulip Priyankara — work permit processing, cannot operate any vehicle |  | Thilafushi | HIGH |  | Open | Do not assign to any vehicle until permit confirmed active.

## 🚛 Fleet Status
WELL LAND INVESTMENT ¦ HEAVY VEHICLE FLEET STATUS REGISTER (WL-REG-002)
31 vehicles total (incl. 8 Al Dahr arrivals + 4 pending delivery) ¦ Rental Eligibility = Thilafushi base ONLY AND status OP/Standby ¦ Thilafushi currently DOWN — no vehicles eligible
⚠ RENTAL RULE: Only vehicles at THILAFUSHI BASE with status Operational or Standby are eligible for rent. ALL project-site vehicles are EXCLUDED. Thilafushi is currently DOWN — rental eligibility = 0 until base is operational.
Fleet ID | Vehicle Type | Brand | Model | Current Location | Assigned Project | Operator Assigned | Status | Condition | Rental Eligible? | Daily Report Rcvd? | Fuel % | Open PR Ref | Known Issue | Issue History | Reg No. | Chassis No. | Engine No. | Last Maintenance | Next Maint Due
WL-HV-0001 | Hauler Dump Truck | VOLVO | A40G | Bodufinolhu |  |  | Active — Site | Good | [6 empty] | N/A
WL-HV-0002 | Hauler Dump Truck | VOLVO | A40G | Thilafushi — Base |  |  | Active — Site | Good |  |  |  |  | SCR Delete procedure service (Completed) |  | N/A
WL-HV-0003 | Dump Truck | ISUZU | 14 Tons | Thilafushi — Base |  |  | Active — Site | Good | [6 empty] | N/A
WL-HV-0004 | Dump Truck | UD NISSAN | 14 Tons | Thilafushi — Base |  |  | Active — Site | Good | [6 empty] | N/A
WL-HV-0005 | High Bed Excavator | KOBELCO | SK380 | Muthaafushi | Muthaafushi Resort Development |  | Operational | Minor Issue |  |  |  |  | Air filter due — can be cleaned and reused. Schedule cleaning at next available opportunity. |  | N/A |  |  | 20/04/2026
WL-HV-0006 | Low Bed Excavator | KOMATSU | PC350 | Muthaafushi | Muthaafushi Resort Development |  | Grounded | Issue |  |  |  |  | GROUNDED — Multiple active faults (20 Apr 2026): ① Engine oil hose burst — hose sent to Malé workshop for fabrication. 2 nos to be dispatched via B.Atoll ferry 22 Apr → Thulhaadhoo → Idrees → site. ② Pilot block failed after only 4 hrs post-repair. IEPL quote: USD 1,050 CNF Malé (IEPL-EX-QT-004/26-27). MVR quote requested. ③ Solenoid valve ×2 — 1 nos in hand at site, 1 nos on order. Quoted MVR 7,992 for set. ④ Hydraulic main filter — replacement dispatched (1 nos). ⑤ Hydraulic strainer filter — dispatched to site (1 nos). Logistics: All parts via B.Atoll ferry → Thulhaadhoo → collected by Idrees → site. | 1. Pilot block failed — failed after 4 hrs post-repair; replacement parts being sourced 2. Solenoid valve x2 required — 1 in hand, 1 on order 3. Hydraulic main filter — replacement dispatched (1 nos) 4. Hydraulic strainer filter — dispatched to site (1 nos) | N/A |  |  | 20/04/2026
WL-HV-0007 | High Bed Excavator | KOMATSU | PC350 | Bodufinolhu | Bodufinolhu Resort Development |  | Grounded | Issue |  |  |  |  | GROUNDED — Main hydraulic pump failure (20 Apr 2026): Tandem pump — one side failed. Pump internals photographed and inspected on site (Mar 2026, Mr. Venkata / IEPL). Recommendation: Replace with reconditioned pump. Quote: USD 6,000 via IEPL (Mr. Hari Pilla). Lead time ~30 days. Decision pending management approval (Hameed). Interim option: repair using salvaged components from previously disassembled pump. NOTE: New pump NOT recommended — aged hydraulic circuit cannot sustain full pump pressure; cascade failure risk on hoses, seals and valves. Engineer Mr. Venkata (IEPL) on site — MVR 800/day accruing from 13 Apr 2026. |  | N/A |  |  | 20/04/2026
WL-HV-0007 | Low Bed Excavator | KOMATSU | PC350 | Bodufinolhu | Bodufinolhu Resort Development |  | Grounded | Issue |  |  |  |  | STANDBY — Parts being sourced (identified by IEPL engineer Mr. Venkata): ① Wiring fault — diagnosed and corrected by Venkata on site. ✓ Resolved. ② Hydraulic line adapter / elbow fitting — no standard part available. Fabricated at Ex Ceylon Engineering, Malé. Dispatching 22 Apr ferry → Thulhaadhoo → Idrees → site. ③ Solenoid valve ×2 — 1 nos held by Venkata at site (payment outstanding, MVR 7,992 for set). 1 nos on order. ④ Pilot block (3-bolt) — failed after 4 hrs. IEPL quote USD 1,050 CNF Malé. MVR quote requested. Machine can resume partial operation once adapter and solenoid installed. | Wiring issue — corrected by Infra Engineers India engineer (Mr. Venkata) on site. ✓ Hydraulic line adapter identified by Venkata — sample sent to Malé, fabricated at Ex Ceylon Engineering; ready for dispatch on 22 Apr ferry → Thulhaadhoo → Idrees → site. Solenoid valve x2 — required, being sourced. Machine on standby pending adapter and solenoid installation. | N/A |  |  | 20/04/2026
WL-HV-0008 | High Bed Excavator | KOMATSU | PC350 | Bodufinolhu | Bodufinolhu Resort Development |  | Operational | Minor Issue |  |  |  |  | Hydraulic jack line issue — arm and boom seal kits dispatched ~15 Apr 2026. Repair in progress. Machine operational at reduced capacity while seals replaced. Advisory: Procure one spare reconditioned hydraulic pump as buffer stock. Pump wear pattern on this aged machine indicates imminent failure risk. |  | N/A |  |  | 20/04/2026
WL-HV-0009 | Low Bed Excavator | KOMATSU | PC350 | Unknown — verify urgently |  |  | Unknown | Unknown |  |  |  |  | ⚠ Location and current status unconfirmed. Verify with Sampath / Janaka urgently. |  | N/A |  |  | 20/04/2026
WL-HV-0010 | Mobile Crane | TADANO | TR300EX | Thilafushi — Base |  |  | Operational | Minor Issue | [6 empty] | N/A
WL-HV-0011 | Low Bed Excavator | KOBELCO | SK235 | Muthaafushi | Muthaafushi Resort Development |  | Operational | Good | [6 empty] | N/A
WL-HV-0012 | Low Bed Excavator | KUBOTA | 50 | Muthaafushi | Muthaafushi Resort Development |  | Operational | Good | [6 empty] | N/A
WL-HV-0013 | Forklift | NISSAN | 5 Tons | Thilafushi — Base |  |  | Operational | Good | [6 empty] | N/A
WL-HV-0014 | Bobcat | BOBCAT | S450 | Thilafushi — Base |  |  | Operational | Good | [6 empty] | N/A
WL-HV-0015 | Pickup | AF | 6 Tons | Thilafushi — Base |  |  | Operational | Good | [6 empty] | N/A
WL-HV-0016 | Loader | CAT | — | Muthaafushi | Muthaafushi Resort Development |  | Operational | Good | [6 empty] | N/A
WL-HV-0017 | Wheel Excavator (New) | XCMG | XE60WG | Thilafushi — Base |  |  | Operational | Good |  |  |  |  | ARRIVED — Al Dahr / Rolman PI93510 — EX#1488 — |  | N/A | XUGD060FCRKA00001 | G4GYMCL029F31
WL-HV-0018 | Tracked Excavator (New) | KOMATSU | PC70-8 | Thilafushi — Base | Alia Investment (Thilafushi) |  | Operational | Issue |  |  |  |  | Track line damaged — no standard off-shelf part available in Maldives. Fabrication from Teflon material. Check RKL Maldives for Teflon supply. Custom fabrication in progress. |  | N/A | KMTPC238P38C02085 | SAA4D95LE-5 | 20/04/2026
WL-HV-0019 | CAT Excavator (New) | CATERPILLAR | 323D3 | Thilafushi — Base |  |  | Operational | Good | [6 empty] | N/A | CAT0323DKFEY00469 | ?
WL-HV-0020 | SUMITOMO Excavator (New) | SUMITOMO | SH220LC6 | Thilafushi — Base |  |  | Operational | Good | [6 empty] | N/A | SMT220U6P00BH1182
WL-HV-0021 | CAT 336DL Excavator (New) | CATERPILLAR | 336DL | Thilafushi — Base |  |  | Grounded | Issue |  |  |  |  | No Bucket |  | N/A | CAT0336DAWRK00437 | THX41079
WL-HV-0022 | CAT 336DL Excavator (New) | CATERPILLAR | 336DL | Thilafushi — Base |  |  | Grounded | Issue |  |  |  |  | No Bucket |  | N/A | CAT0336DPPGW00178 | THX37812
WL-HV-0023 | CAT 745C ARTICULATED DUMPTRUCK (New) | CATERPILLAR | 745C | Bodufinolhu | Bodufinolhu Resort Development |  | Grounded | Issue |  |  |  |  | Power Issue: Work around - bypassing/manual wire short ignition Sampath requested to send our electrician Lakmal from Thilafushi to Bodufinolhu to troubleshoot and correct the issue |  | N/A | CAT0745CETFK00507 | C18-7MRO5738
WL-HV-0024 | CAT 745C ARTICULATED DUMPTRUCK (New) | CATERPILLAR | 745C | Thilafushi — Base |  |  | Operational | Good |  |  |  |  | Switch Assembly Issue: Parts received; Status OK |  | N/A | CAT0745CTTFK00218 | C18-7MRO3619
WL-HV-0025 | Mini Excavator (Al Dahr) | YANMAR | B65 | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N13 ¦ 2016 ¦ Japan ¦ 2,698 Hrs ¦ AED 100,000 NOT YET RECEIVED |  | N/A | YMRB65YYAEYC10535
WL-HV-0026 | Forklift — Pneumatic Tyre (Al Dahr) | DOOSAN | D505C-5 | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N3 ¦ RW EX#1004 ¦ 2022 ¦ Korea ¦ Brand New ¦ AED 145,000 NOT YET RECEIVED |  | — | FDB08113001920
WL-HV-0027 | Tracked Excavator (Al Dahr) | KOMATSU | PC70-8 | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N6 ¦ RW EX#517 ¦ 2012 ¦ Japan ¦ 4,873 Hrs ¦ AED 80,000 NOT YET RECEIVED |  | — | KMTPC238L38C02550
WL-HV-0028 | 8x4 Sleeper Dump Truck (Al Dahr — Ordered) | XCMG | XGA3310D6NEX | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N4 ¦ RW EX#1725 ¦ 2021 ¦ China ¦ Unused ¦ AED 170,000 — NOT YET RECEIVED |  | — | LC1HNRBG6M0003592
WL-HV-0029 | 8x4 Sleeper Dump Truck (Al Dahr — Ordered) | XCMG | XGA3310D6NEX | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N5 ¦ RW EX#1726 ¦ 2021 ¦ China ¦ Unused ¦ AED 170,000 — NOT YET RECEIVED |  | — | LC1HNRBG8M0003593
WL-HV-0030 | Rough Terrain Crane (Al Dahr — Ordered) | GROVE | RT700E | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N9 ¦ RW EX#1527 ¦ 2007 ¦ USA ¦ 4,050 Hrs ¦ AED 392,000 — NOT YET RECEIVED |  | — | RT700E#227269
WL-HV-0031 | 48T Straight Boom Crane / Flatbed (Al Dahr — Ordered) | XCMG / DONGFENG | SQS200 | Pending Delivery |  |  | Ordered — Pending Delivery | — | ✗ No |  |  |  | PENDING — Al Dahr / Rolman PI93510 S/N12 ¦ RW EX#1622 ¦ 2023 ¦ China ¦ 1,186 Km ¦ AED 185,000 — NOT YET RECEIVED |  | — | LGHCHD1P8P6102757
Shajalal - 796-0820

## ⚓ Marine Vessels
WELL LAND INVESTMENT ¦ MARINE VESSELS REGISTER (WL-REG-MARINE-001)
4 vessels ¦ Captains submit daily status ¦ Permit/Insurance expiry dates MUST be filled — auto-alerts at 60 days
Vessel ID | Name/Ref | Type | Status | Drydocked? | Captain in Charge | Crew Assigned | Reg No. | Hull / IMO | Engine 1 Serial | Engine 2 Serial | Capacity/Notes | Permit No. | Permit Expiry | Insurance Expiry | Last Inspection | DryDock Start | DryDock Est. End | Known Issues / Notes
WL-MV-0001 | LCT 1 | LCT | Active | No | Ali Shameem (WL-EMP-0001) | Anuar Hussain, Mohammad Jakir Hossain, Sheikh Mohamed Farid Miah, Easa Gasim |  |  |  |  | LCT cargo vessel
WL-MV-0002 | Dhoni 1 | Dhoni/Ferry | Active | No | Nasrulla Ali (WL-EMP-0003) | MD Robel Miah, Ala Uddin, Mokhles, Yeasin Miah |  |  |  |  | Ferry / supply runs
WL-MV-0003 | Speed Boat 1 | Speed Boat | Running | No | Jakir Hossain (WL-EMP-0011) | [5 empty] | Fast passenger/cargo
WL-MV-0004 | Speed Boat 2 | Speed Boat | Drydocked | Yes | — | [12 empty] | ⚠ VERIFY: Same boat as SB1 at different time, or separate vessel? Confirm with Janaka.
| well land heavy | barge | Active | No

## 👥 Staff Register
ANTRAC HOLDING / WELL LAND INVESTMENT ¦ STAFF MASTER REGISTER
31 engaged ¦ Add new staff in next empty row ¦ Fill permit expiry — auto-highlights red at 30 days ¦ Updated by: Well Land Ops
Staff ID | Full Name | Designation | Nationality | Grade | Joined Date | Category | Operator? | Status | Current Location | Assigned Asset/Vessel | Permit No. | Permit Expiry | Work Permit Status | Contact No. | Notes
WL-EMP-0001 | Ali Shameem | Senior Captain | Local/Maldivian | G8 | 01/02/2012 | Marine | No | Full Time
WL-EMP-0002 | Anuar Hussain | Crew, LCT 1 | Expat/Bangladeshi | G6 | 08/09/2015 | Marine | No | Full Time
WL-EMP-0003 | Nasrulla Ali | Senior Captain | Local/Maldivian | G8 | 13/04/2016 | Marine | No | Full Time
WL-EMP-0004 | Shahjalal | Driver Cum Asst Mechanic | Expat/Bangladeshi | G6 | 17/05/2016 | Land/Terminal | Yes | Full Time
WL-EMP-0005 | MD Robel Miah | Crew, Tug Boat | Expat/Bangladeshi | G6 | 17/05/2016 | Marine | No | Full Time
WL-EMP-0006 | Mohammad Jakir Hossain | Crew, LCT 1 | Expat/Bangladeshi | G6 | 04/06/2016 | Marine | No | Full Time
WL-EMP-0007 | R L Walapita Godellage | Crane Operator | Expat/Sri Lankan | G5 | 15/05/2017 | Land/Terminal | Yes | Full Time
WL-EMP-0008 | Mohammad Nurul Amin | Welder | Expat/Bangladeshi | G6 | 31/05/2017 | Land/Terminal | No | Full Time
WL-EMP-0009 | Janaka Prasath Ekanayake | Senior Supervisor | Expat/Sri Lankan | G3 | 30/01/2018 | Land/Terminal | No | Full Time
WL-EMP-0010 | Sheikh Mohamed Farid Miah | Crew, LCT 1 | Expat/Bangladeshi | G5 | 16/06/2019 | Marine | No | Full Time
WL-EMP-0011 | Jakir Hossain | Crew, Speed Boat | Expat/Bangladeshi | G8 | 13/10/2018 | Marine | No | Full Time
WL-EMP-0012 | Ala Uddin | Crew, Tug Boat | Expat/Bangladeshi | G5 | 26/04/2018 | Marine | No | Full Time
WL-EMP-0013 | Ibrahim Mohamed | Supervisor Cum Mechanic | Local/Maldivian | G2 | 01/01/2024 | Land/Terminal | No | Full Time
WL-EMP-0014 | Mokhles | Crew, Tug Boat | Expat/Bangladeshi | G1 | 14/03/2024 | Marine | No | Full Time
WL-EMP-0015 | Mohammad Naim | Terminal Staff | Expat/Bangladeshi | G1 | 23/03/2024 | Land/Terminal | No | Full Time
WL-EMP-0016 | Asif Mia | Terminal Staff | Expat/Bangladeshi | G1 | 23/03/2024 | Land/Terminal | No | Full Time
WL-EMP-0017 | MD Kamrul Islam | Helper | Expat/Bangladeshi | G1 | 22/12/2024 | Land/Terminal | No | Full Time
WL-EMP-0018 | Yeasin Miah | Crew, Tug Boat | Expat/Bangladeshi | G1 | 14/02/2025 | Marine | No | Full Time
WL-EMP-0019 | MD Moyna Mia | Heavy Vehicle Driver | Expat/Bangladeshi | G1 | 21/05/2025 | Land/Terminal | Yes | Full Time
WL-EMP-0020 | Eswararao Chekka | Excavator Operator | Expat/Indian | G1 | 29/07/2025 | Land/Terminal | Yes | Full Time
WL-EMP-0021 | Soundarraj Muniyappan | Excavator Operator | Expat/Indian | G1 | 29/07/2025 | Land/Terminal | Yes | Full Time
WL-EMP-0022 | Abdul Haq | Helper | Expat/Bangladeshi | G1 | 02/08/2025 | Land/Terminal | No | Full Time
WL-EMP-0023 | MD Ramjan Mia | Helper | Expat/Bangladeshi | G1 | 26/08/2025 | Land/Terminal | No | Full Time
WL-EMP-0024 | MD Sayed Mia | Carpenter | Expat/Bangladeshi | G1 | 26/08/2025 | Land/Terminal | No | Full Time
WL-EMP-0025 | Uzzal Sutradhar | Carpenter | Expat/Bangladeshi | G1 | 26/08/2025 | Land/Terminal | No | Full Time
WL-EMP-0026 | Anish John | Excavator Operator | Expat/Indian | G1 | 24/11/2025 | Land/Terminal | Yes | Probation
WL-EMP-0027 | Easa Gasim | Crew, LCT 1 | Local/Maldivian | G1 | 02/12/2025 | Marine | No | Probation
WL-EMP-0028 | Jackson Ndirangu Nginga | Mechanic | Expat/Kenyan | G1 | 23/12/2025 | Land/Terminal | No | Probation
WL-EMP-0029 | Feroskhan Meerasa | Excavator Operator | Expat/Indian | G1 | 29/12/2025 | Land/Terminal | Yes | Probation
WL-EMP-0030 | Ali Mushthaq Ibrahim | Well Land Ops / GM | Local/Maldivian | G0 | 17/01/2026 | Management | No | Probation
WL-EMP-0031 | Dulip Priyankara | Heavy Vehicle Driver | Expat/Indian | G0 | — | Land/Terminal | Yes | Probation |  |  |  |  | Work Permit Processing
WL-EMP-0032
WL-EMP-0033
WL-EMP-0034
WL-EMP-0035
WL-EMP-0036
WL-EMP-0037
WL-EMP-0038
WL-EMP-0039
WL-EMP-0040

## 🔧 Operators
WELL LAND INVESTMENT ¦ VEHICLE OPERATORS & ASSIGNMENT REGISTER
8 operators/drivers ¦ Assign asset IDs when known ¦ Verify location daily
Staff ID | Full Name | Operator Role | Nationality | Grade | Status | Current Location | Assigned Asset ID | Asset Description | Licence No. / Class | Notes
WL-EMP-0004 | Shahjalal | Driver Cum Asst Mechanic | Expat/Bangladeshi | G6 | Full Time
WL-EMP-0007 | R L Walapita Godellage | Crane Operator | Expat/Sri Lankan | G5 | Full Time | Thilafushi | WL-HV-0010 | TADANO TR300EX
WL-EMP-0019 | MD Moyna Mia | Heavy Vehicle Driver | Expat/Bangladeshi | G1 | Full Time
WL-EMP-0020 | Eswararao Chekka | Excavator Operator | Expat/Indian | G1 | Full Time
WL-EMP-0021 | Soundarraj Muniyappan | Excavator Operator | Expat/Indian | G1 | Full Time
WL-EMP-0026 | Anish John | Excavator Operator | Expat/Indian | G1 | Probation
WL-EMP-0029 | Feroskhan Meerasa | Excavator Operator | Expat/Indian | G1 | Probation
WL-EMP-0031 | Dulip Priyankara | Heavy Vehicle Driver | Expat/Indian | G0 | Probation |  |  |  | Work Permit Processing — cannot operate

## 📋 Janaka Daily Log
WELL LAND INVESTMENT ¦ JANAKA DAILY ACTIVITY REPORT — THILAFUSHI BASE
JANAKA: Fill this sheet daily and send screenshot to Well Land Ops by 18:00 ¦ Each row = one vehicle or vessel event that day
HOW TO USE: Each row = one event (vehicle status, issue, ferry trip, PR request, delivery received, staff note). Fill Date, Type, Asset ID, Location, Description, and your name. For PR requests: fill Urgency and Part/Item Needed columns. Send screenshot or photo to Well Land Ops WhatsApp by 18:00 daily. URGENCY CODES: CR = Critical (work stopped) UR = Urgent (24-48hr delay) RO = Routine TYPE CODES: VEH = Vehicle Status Update PR = Parts Request DEL = Delivery Received VSSL = Vessel Update STAFF = Staff Event SITE = Site Update OTHER
Date | Type | Asset ID | Asset Type | Location | Status / Description | Urgency | Part/Item Needed | Qty | Operator / Captain | Fuel Level % | Hours/Reading | Reported By | WL Ops Actioned?
15/03/2026 | PR | WL-HV-0002 | Hauler Dump Truck | Muthaafushi | Hydraulic control valve and hose leaking — machine operational but requires repair soon | CR | Hydraulic control valve + hose — VOLVO A40G | 1 set | — |  |  | Janaka
15/03/2026 | PR | WL-HV-0008 | High Bed Excavator | Unknown | Hose burst on 7 March — machine grounded — parts needed to restart | CR | Hydraulic hose — KOMATSU PC350 | 1 | — |  |  | Sampath (via Janaka)
04/04/2026 | SITE | IEPL | Engineer | Bodufinolhu | Mr. Venkata (IEPL field engineer) deployed to site by Mr. Hari Pilla (IEPL). FOC basis. Assigned to Komatsu PC350 fleet service. | RO | [5 empty] | Mushthaq | Yes
13/04/2026 | SITE | IEPL | Engineer | Bodufinolhu | IEPL FOC period ended. Engineer charges of MVR 800/day now apply. Escalated to management. | UR | [5 empty] | Mushthaq | Escalated to Hameed
15/04/2026 | DEL | WL-HV-0008 | High Bed Excavator | Bodufinolhu | Arm and boom cylinder seal kits dispatched — en route via ferry. | UR | Arm & boom seal kits — KOMATSU PC350 | 1 set |  |  |  | Mushthaq | Yes
20/04/2026 | VEH | WL-HV-0007 | High Bed Excavator | Bodufinolhu | Pilot block replaced. Machine operated approx. 4 hrs. Pilot block failed again. Machine grounded. | CR | [5 empty] | Sampath | Yes — sourcing replacement
20/04/2026 | VEH | WL-HV-0007 | High Bed Excavator | Bodufinolhu | Main hydraulic pump — one side failed. Machine grounded. Pump disassembled and inspected by Venkata (IEPL). Recon pump replacement recommended (USD 6,000 / ~30 days lead time). Decision pending Hameed. | CR | Reconditioned hydraulic pump — KOMATSU PC350 | 1 |  |  |  | Sampath | Pending management decision
20/04/2026 | VEH | WL-HV-0006 | Low Bed Excavator | Muthaafushi | Engine oil hose burst. Machine grounded immediately. Hose sent to Malé workshop for fabrication. 2 nos to be made and dispatched. | CR | Engine oil hose ×2 — KOMATSU PC350 | 2 |  |  |  | Sampath | Yes — fabrication in progress
22/04/2026 | DEL | WL-HV-0006 / WL-HV-0007 | Excavator | B.Atoll Ferry → Thulhaadhoo → Idrees → site | DISPATCH: Engine oil hose ×2 (for WL-HV-0006) + hydraulic line adapter ×1 (for WL-HV-0007) sent via B.Atoll ferry. Idrees to collect at Thulhaadhoo and deliver to site. | CR | Engine oil hose ×2 / Hydraulic adapter ×1 | 3 items |  |  |  | Mushthaq | Pending delivery confirmation

## 📦 PR Log
ANTRAC HOLDING ¦ PURCHASE REQUEST LOG (WL-REG-001) — Well Land · MPL · Other
Log EVERY PR: from Thilafushi, Sampath, or any site. CRITICAL = same-day action. All quotes + PO filed physically.
UNIT COLOUR: ■ Well Land = Blue tint ■ PLK (Petroleum Link) = Orange tint ■ Both/Other = Grey URGENCY: ■ CRITICAL = Red ■ URGENT = Amber ■ ROUTINE = White
PR Ref | Date | Business Unit | Raised By | Site / Location | Item(s) Summary | Vehicle / Asset Ref | Urgency | # Quotes | PO No. | FC Approved? | Vendor | Date Ordered | Dispatched? | Delivered? | Status / Notes
WL-PR-0001 | 15/03/2026 | Well Land | Janaka / Sampath | Muthaafushi | Hydraulic control valve + hose — Hauler Dump Truck VOLVO A40G | WL-HV-0002 | CRITICAL | [7 empty] | Open — obtain quotes
WL-PR-0002 | 15/03/2026 | Well Land | Sampath (via Janaka) | Unknown | Hydraulic hose burst — High Bed Excavator KOMATSU PC350 | WL-HV-0008 | CRITICAL | [7 empty] | Open — verify location, obtain quotes
WL-PR-0003 | 08/04/2026 | Well Land | Mushthaq / Hari (IEPL) | Bodufinolhu & Muthaafushi | Pilot Block — KOMATSU PC350-7. IEPL-EX-QT-004/26-27 dated 08 Apr 2026. USD 800 part + USD 250 air freight = USD 1,050 CNF Malé. MVR equivalent quote requested. | WL-HV-0006 / WL-HV-0007 | CRITICAL | 1 |  |  | Infra Engineers India (Mr. Hari Pilla) | 08/04/2026 | No | No | Quote received. Awaiting MVR quote and management approval. Note: Sri Lanka supplier previously quoted MVR 3,785 (new part) — significantly lower.
WL-PR-0004 | 20/04/2026 | Well Land | Venkata (IEPL) / Mushthaq | Bodufinolhu | Hydraulic pump solenoid valve ×2 — KOMATSU PC350. 1 nos held by Venkata at site. 1 nos to order. Total MVR 7,992. | WL-HV-0007 | CRITICAL | 1 |  |  | Infra Engineers India (Mr. Hari Pilla) | 20/04/2026 | Partial | Partial | 1 nos physically at site with Venkata — payment outstanding. 1 nos to be ordered. Resolve payment to release part.
WL-PR-0005 | 20/04/2026 | Well Land | Venkata (IEPL) / Mushthaq | Bodufinolhu | Hydraulic line adapter / elbow fitting — KOMATSU PC350. No standard part available in Maldives. Custom fabrication at Ex Ceylon Engineering, Malé. | WL-HV-0007 | URGENT | 0 |  |  | Ex Ceylon Engineering (fabrication) | 20/04/2026 | Yes — 22 Apr ferry | No | Part fabricated and ready. Dispatching 22 Apr via B.Atoll ferry → Thulhaadhoo → Idrees → site.
WL-PR-0006 | 20/04/2026 | Well Land | Sampath | Muthaafushi | Engine oil hose ×2 — KOMATSU PC350. Hose burst 20 Apr 2026. Sent to Malé workshop for fabrication. | WL-HV-0006 | CRITICAL | 0 |  |  | Workshop Malé (fabrication) | 20/04/2026 | Yes — 22 Apr ferry | No | Fabrication in progress. 2 nos to be dispatched via B.Atoll ferry 22 Apr → Thulhaadhoo → Idrees → site.
WL-PR-0007 | Apr 2026 | Well Land | Venkata (IEPL) / Mushthaq | Muthaafushi | Hydraulic main filter — KOMATSU PC350. 1 nos replacement dispatched to site. | WL-HV-0006 | URGENT | [5 empty] | Yes | Pending confirmation | Dispatched. Confirm receipt with Sampath / Janaka.
WL-PR-0008 | Apr 2026 | Well Land | Venkata (IEPL) / Mushthaq | Muthaafushi | Hydraulic strainer filter — KOMATSU PC350. 1 nos dispatched to site. | WL-HV-0006 | URGENT | [5 empty] | Yes | Pending confirmation | Dispatched. Confirm receipt with Sampath / Janaka.
WL-PR-0009 | 15/04/2026 | Well Land | Sampath / Mushthaq | Bodufinolhu | Arm and boom cylinder seal kits — KOMATSU PC350. Dispatched approx. 15 Apr 2026. | WL-HV-0008 | URGENT |  |  |  |  | 15/04/2026 | Yes | Pending confirmation | Dispatched ~5 days ago. Repair in progress on site. Confirm receipt and installation status with Sampath.
WL-PR-0010 | 20/04/2026 | Well Land | Mushthaq | Bodufinolhu | Reconditioned main hydraulic pump — KOMATSU PC350 (Part No. 708-2G-00024). Quoted USD 6,000 via IEPL. Shipping lead time ~30 days. | WL-HV-0007 | CRITICAL | 1 |  | Pending | Infra Engineers India (Mr. Hari Pilla) |  | No | No | PENDING MANAGEMENT DECISION (Hameed). New pump not recommended — cascade failure risk on aged circuit. Reconditioned preferred. Engineer cost MVR 800/day accruing from 13 Apr 2026.
WL-PR-0011 | 20/04/2026 | Well Land | Janaka | Thilafushi | Track line — KOMATSU PC70-8 (WL-HV-0018). No standard part. Fabrication from Teflon material. Source: RKL Maldives. | WL-HV-0018 | URGENT | 0 |  |  | RKL Maldives (supply) + Workshop (fabrication) |  | No | No | Custom fabrication required. Check RKL Maldives for Teflon stock. In progress.

## 💰 Rental Log
WELL LAND INVESTMENT ¦ RENTAL INQUIRY & SALES CONVERSION LOG (WL-REG-003)
Every inquiry logged — available or not ¦ Rental = Thilafushi base ONLY ¦ Currently ZERO eligible (base down) ¦ Sales target: set monthly
⚠ AVAILABILITY RULE: Before confirming any rental, verify Fleet Status sheet — vehicle must be at THILAFUSHI BASE with status Operational or Standby. Project-site vehicles CANNOT be rented. When Thilafushi base is operational, check for verified conditions (not Unknown) before quoting.
Inquiry Ref | Date | Customer | Contact | Vehicle Type Requested | Duration / Dates | Site | Available? | Unavailability Reason | Quotation Sent? | Confirmed? | Quoted Amt (MVR) | Actual Amt (MVR) | Decline Reason / Notes

## 📂 Document Vault
WELL LAND INVESTMENT ¦ ASSET DOCUMENT VAULT — Vehicles · Vessels · Registration · Insurance · Compliance
Collect and log all documents for every asset ¦ Required for rental customers ¦ Required for compliance ¦ ⚠ = missing/expired
PART A — HEAVY VEHICLES (Documents required per vehicle: Registration, Insurance, Owner Manual, Service History, Operator Licence Compliance)
Fleet ID | Vehicle Type | Brand / Model | Registration No. | Chassis No. | Engine No. | Insurance Policy No. | Insurance Expiry | Reg Expiry | Owner Manual? | Service Records? | Operator Cert Required? | Last Service Date | Document Location / Notes
WL-HV-0001 | Hauler Dump Truck | VOLVO A40G | [6 empty] | No | No |  |  | ⚠ At Bodufinolhu site. Condition unverified. Inspect before any rental.
WL-HV-0002 | Hauler Dump Truck | VOLVO A40G | [6 empty] | No | No |  |  | SCR delete procedure completed (Apr 2026). Known issue: hydraulic control valve/hose leaking — PR WL-PR-0001 open.
WL-HV-0003 | Dump Truck | ISUZU 14T | [6 empty] | No | No |  |  | ⚠ Condition unverified — inspect before renting.
WL-HV-0004 | Dump Truck | UD NISSAN 14T | [6 empty] | No | No |  |  | ⚠ Condition unverified — inspect before renting.
WL-HV-0005 | Low Bed Excavator | KOBELCO SK380 | [6 empty] | No | No |  |  | Muthaafushi. Operational. Air filter due — can be cleaned. Obtain service records.
WL-HV-0006 | Low Bed Excavator | KOMATSU PC350 | [6 empty] | No | No |  |  | GROUNDED. Multiple faults: engine oil hose, pilot block, solenoid, filters. Obtain full service history. See Fleet Status WL-HV-0006.
WL-HV-0007 | Low Bed Excavator | KOMATSU PC350 | [6 empty] | No | No |  |  | GROUNDED. Hydraulic pump failure + pilot block + solenoid + adapter faults. Obtain full service history. See Fleet Status WL-HV-0007. Note: purchased used — Hari Pilla (IEPL) was original supplier.
WL-HV-0008 | High Bed Excavator | KOMATSU PC350 | [6 empty] | No | No |  |  | Operational (minor issue). Arm/boom seals being replaced. Obtain service records.
WL-HV-0009 | High Bed Excavator | KOMATSU PC350 | [6 empty] | No | No |  |  | ⚠ Location unknown — verify with Sampath / Janaka. Obtain service records once located.
WL-HV-0010 | Mobile Crane | TADANO TR300EX | [6 empty] | No | No |  |  | Operational at Thilafushi. Minor issue noted. Obtain service records.
WL-HV-0011 | Low Bed Excavator | KOBELCO SK235 | [6 empty] | No | No |  |  | Operational at Muthaafushi. Obtain service records.
WL-HV-0012 | Low Bed Excavator | KUBOTA 50 | [6 empty] | No | No |  |  | Operational at Muthaafushi. Obtain service records.
WL-HV-0013 | Forklift | NISSAN 5T Forklift | [6 empty] | No | No |  |  | Operational at Thilafushi. Obtain service records.
WL-HV-0014 | Bobcat | BOBCAT S450 | [6 empty] | No | No |  |  | Operational at Thilafushi. Obtain service records.
WL-HV-0015 | Pickup | AF 6T Pickup | [6 empty] | No | No |  |  | Operational at Thilafushi. Obtain service records.
WL-HV-0016 | Loader | CAT Loader | [6 empty] | No | No |  |  | Operational at Muthaafushi. Obtain service records.
WL-HV-0017 | Excavator (New) | XCMG XE60WG |  | XUGD060FCRKA00001 | G4GYMCL029F31 |  |  |  | No | No |  |  | Al Dahr / Rolman PI93510 EX#1488. Arrived Thilafushi. ⚠ Obtain registration, insurance, owner manual urgently.
WL-HV-0018 | Excavator (New) | KOMATSU PC70-8 |  | KMTPC238P38C02085 | SAA4D95LE-5 |  |  |  | No | No |  |  | Assigned to Alia Investment (Thilafushi). Track line damaged — Teflon fabrication in progress (check RKL Maldives). ⚠ Obtain all docs.
WL-HV-0019 | Excavator (New) | CAT 323D3 |  | CAT0323DKFEY00469 | — (to confirm) |  |  |  | No | No |  |  | New unit at Thilafushi. ⚠ Engine No. to be confirmed. Obtain all docs urgently.
WL-HV-0020 | Excavator (New) | SUMITOMO SH220LC6 |  | SMT220U6P00BH1182 |  |  |  |  | No | No |  |  | New unit at Thilafushi. ⚠ Obtain all docs urgently.
PART B — MARINE VESSELS (Registration, Survey Certificate, Seafarer Permits, Insurance, Permit from MNDF/MPA)
Vessel ID | Name | Type | Reg No. | Hull/IMO | Survey Cert No. | Survey Expiry | Permit No. (MNDF/MPA) | Permit Expiry | Insurance No. | Insurance Expiry | Captain Cert No. | Last Survey Date | Document Status / Notes
WL-MV-0001 | LCT 1 | LCT | [9 empty] | Ali Shameem
WL-MV-0002 | Dhoni 1 | Dhoni/Ferry | [9 empty] | Nasrulla Ali
WL-MV-0003 | Speed Boat 1 | Speed Boat | [9 empty] | Jakir Hossain
WL-MV-0004 | Speed Boat 2 | Speed Boat | [9 empty] | — | ⚠ Drydocked — verify identity before any activity

## 📅 Compliance
WELL LAND INVESTMENT ¦ COMPLIANCE & GOVERNMENT FEES CALENDAR
Track ALL renewals: permits, GST, BPT, work permits, insurance, vessel surveys, vehicle registrations ¦ ⚠ = due within 60 days
All amounts in MVR. Dates auto-highlight RED when within 60 days of due date. Add new rows as needed. Source documents filed in Document Vault sheet.
Ref | Category | Description | Entity | Asset / Ref | Frequency | Last Paid / Filed | Amount (MVR) | Next Due Date | Lead Time Needed | Responsible | Status / Notes
1 | Vehicle Reg | Vehicle Registration Renewal | Well Land | All vehicles (do per asset) | Annual |  |  |  | 30 days | Well Land Ops | Fill per vehicle
2 | Vehicle Reg | Vehicle Insurance Renewal | Well Land | All vehicles (do per asset) | Annual |  |  |  | 30 days | Well Land Ops | Fill per vehicle
3 | Vessel | Vessel Survey Certificate — LCT 1 | Well Land | WL-MV-0001 | Annual/Biennial |  |  |  | 30 days | Well Land Ops | MPA / MNDF — obtain current status
4 | Vessel | Vessel Survey Certificate — Dhoni 1 | Well Land | WL-MV-0002 | Annual/Biennial |  |  |  | 30 days | Well Land Ops | MPA / MNDF
5 | Vessel | Vessel Survey Certificate — Speed Boat 1 | Well Land | WL-MV-0003 | Annual/Biennial |  |  |  | 30 days | Well Land Ops | MPA / MNDF
6 | Vessel | Vessel Permit — LCT 1 (MNDF/MPA) | Well Land | WL-MV-0001 | Annual |  |  |  | 30 days | Well Land Ops
7 | Vessel | Vessel Permit — Dhoni 1 (MNDF/MPA) | Well Land | WL-MV-0002 | Annual |  |  |  | 30 days | Well Land Ops
8 | Vessel | Vessel Insurance — LCT 1 | Well Land | WL-MV-0001 | Annual |  |  |  | 30 days | Well Land Ops
9 | Vessel | Vessel Insurance — Dhoni 1 | Well Land | WL-MV-0002 | Annual |  |  |  | 30 days | Well Land Ops
10 | Work Permit | Work Permit — Expat staff (per employee) | Well Land | All expat staff | Annual/Biennial |  |  |  | 30 days | Well Land Ops | ~29 expats — manage per person in Staff sheet
11 | Work Permit | Work Permit — Dulip Priyankara | Well Land | WL-EMP-0031 | — |  |  |  | 30 days | Well Land Ops | Processing — not yet active
12 | Tax | Business Profit Tax (BPT) — Filing | Well Land | Company | Annual |  |  |  | 30 days | Well Land Ops | MRA filing
13 | Tax | GST — Rental Income (if applicable) | Well Land | Rental revenue | Quarterly |  |  |  | 30 days | Well Land Ops | If Well Land is GST registered
14 | Tax | GST — Petroleum Link (PLK) | PLK | Company | Quarterly |  |  |  | 30 days | Well Land Ops | Coordinate with PLK accounts
15 | Compliance | Labour Relations Authority — Staff Register | Well Land | All staff | Annual |  |  |  | 30 days | Well Land Ops | Submit to LRA
16 | Compliance | Immigration — Expat Quota | Well Land | Expat staff | Annual |  |  |  | 30 days | Well Land Ops | Renew quota for expat positions
17 | Compliance | Thilafushi Lease / Land Rent | Well Land | Thilafushi Base | Annual |  |  |  | 30 days | Well Land Ops | Base lease renewal if applicable
18 | Other | Add row for each additional fee → | [6 empty] | 30 days | Well Land Ops

## 📞 Call Log
WELL LAND INVESTMENT ¦ PHONE INQUIRY LOG — ANSWER EVERY CALL · LOG EVERY CALL
This is the number Moosabey managed. Every call is a business event. Log before you do anything.
# | Date | Time | Caller | Company | Call Type | Request / Details | Action | Follow-Up Date | Logged in PR/Rental? | Closed?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## 📅 Daily Log
WELL LAND OPS DAILY LOG ¦ One row per day ¦ Running record of all operational activity
Fill daily — even partial entries. This is your record of what happened and why decisions were made.
Date | PRs Received | Rental Inquiries | Fleet / Vessel Events | Staff Issues | Director Conversations | Purchases / Payments | Escalations / Critical | Compliance Actions | Notes / Tomorrow
15/03/2026 | WL-PR-0001, WL-PR-0002 |  | VOLVO A40G hydraulic hose issue flagged (Muthaafushi). KOMATSU PC350 hose burst 7 Mar reported. |  |  |  | Two CRITICAL PRs raised. Both open. |  | Obtain quotes for both. Verify PC350 location.
04/04/2026 |  |  | IEPL engineer Mr. Venkata deployed to Bodufinolhu — FOC basis, effective today. | [5 empty] | Monitor FOC period — ends 13 Apr.
08/04/2026 | WL-PR-0003 |  | Pilot block quotation received from IEPL — USD 1,050 CNF Malé (IEPL-EX-QT-004/26-27). |  | Reviewed quote with Mr. Hari Pilla (IEPL). |  |  |  | Request MVR equivalent. Compare with Sri Lanka supplier (MVR 3,785 for same part).
13/04/2026 |  |  | IEPL FOC period ended. MVR 800/day engineer charges now accruing. |  |  |  | Engineer cost accruing daily — escalate to Hameed for pump decision ASAP. |  | Push Hameed for decision before further cost accumulates.
15/04/2026 | WL-PR-0009 |  | Arm and boom seal kits dispatched to Bodufinolhu for WL-HV-0008. |  |  | Seal kits purchased and dispatched. |  |  | Confirm receipt with Sampath.
20/04/2026 | WL-PR-0006, WL-PR-0010 |  | WL-HV-0006 engine oil hose burst (Muthaafushi). WL-HV-0007 hydraulic pump failed (Bodufinolhu). Meeting held with Mr. Hari Pilla — Komatsu fleet uptime discussion. Fleet status confirmed: 2 machines down, multiple parts pending. |  | Meeting with Mr. Hari Pilla (IEPL). Fleet situation briefed. To be escalated to Hameed for pump replacement decision. |  | CRITICAL: 2 machines simultaneously down. Pump replacement decision needed urgently. Solenoid payment outstanding. |  | Dispatch parts via ferry 22 Apr. Get Hameed decision today.
22/04/2026 |  |  | DISPATCH: Engine oil hose ×2 + hydraulic adapter ×1 sent via B.Atoll ferry → Thulhaadhoo → Idrees → site. |  |  | Parts dispatched. | Confirm Idrees collects at Thulhaadhoo and delivers to site. |  | Follow up delivery confirmation with Sampath / Janaka.

## ℹ️ Guide
WELL LAND INVESTMENT ¦ OPS REGISTER — GUIDE & QUICK REFERENCE
DAILY ROUTINE
1. Start of day | Open 📅 Daily Log → note today's date. Open 📋 Janaka Daily Log → check if previous day report arrived.
2. Fleet check | Open 🚛 Fleet Status → update any changes from Janaka's WhatsApp report. Key: location + status + any new issues.
3. New PR arrives | 📋 PR Log → add row immediately. Fill urgency. If CRITICAL, act same day — get quotes.
4. Phone rings | 📞 Call Log → log before doing anything. If rental: check 🚛 Fleet Status first, then log in 💰 Rental Log.
5. Rental inquiry | 💰 Rental Log → only quote if vehicle at Thilafushi AND status OP/Standby AND condition verified.
6. Compliance check | 📅 Compliance → weekly scan for any red-highlighted due dates. Act 30+ days ahead.
7. End of day | 📅 Daily Log → fill today's row. Note any carry-forwards.
SHEETS
📊 Dashboard | Overview. KPI boxes for fleet/marine/staff counts. Open actions table — fill manually daily.
🚛 Fleet Status | 20 vehicles. Rental Eligible column is a formula — auto-calculates from Location+Status. Update from Janaka reports.
⚓ Marine Vessels | 4 vessels. Fill permit and insurance expiry dates — auto-alerts at 60 days.
👥 Staff Register | 31 staff + 9 blank rows for new hires. Permit expiry auto-alerts at 30 days.
🔧 Operators | 8 operators. Assign asset IDs when you know who is on which machine.
📋 Janaka Daily Log | Janaka fills this (or screenshots to WhatsApp daily). Well Land Ops updates fleet sheet from it.
📦 PR Log | Every purchase request — Antrac-wide. Unit column colour-coded: blue=Well Land, orange=PLK.
💰 Rental Log | Every rental inquiry. Even when unavailable — log reason. Builds conversion data.
📂 Document Vault | Every document needed per vehicle and vessel. Fill when you collect physical docs.
📅 Compliance | All government fees, permits, taxes, renewals. Fill 'Next Due Date' — auto-highlights red at 60 days.
📞 Call Log | Every call. Log before acting. Links back to PR or Rental log.
📅 Daily Log | One row per day. Your running operational journal.
RENTAL ELIGIBILITY RULES
Rule 1 | ONLY vehicles at THILAFUSHI BASE are ever rental-eligible. Project site vehicles are 100% excluded.
Rule 2 | Thilafushi base is currently DOWN. Rental eligibility = 0 until base is back up.
Rule 3 | Condition must NOT be Unknown before quoting a customer. Verify first, quote after.
Rule 4 | Vehicle status must be Operational or Standby. Grounded, Under Maintenance, etc. = not eligible.
Rule 5 | Rental Eligible column in Fleet sheet is a formula — it auto-calculates. Do not manually override it.
KNOWN ACTIONS (from launch data)
WL-HV-0002 | CRITICAL: VOLVO A40G at Muthaafushi — hydraulic control valve/hose leaking. PR raised as WL-PR-0001.
WL-HV-0008 | CRITICAL: KOMATSU PC350 High Bed — hose burst 7 March. PR raised as WL-PR-0002. Verify location.
WL-HV-0017~20 | 4 new excavators — no brand/model/location yet. Obtain specs and all documentation urgently.
11 vehicles | WL-HV-0005 through 0016 (exc. 0010, 0013, 0015) — location and condition unknown. Verify with Janaka.
WL-MV-0004 | Speed Boat 2 drydocked — verify with Janaka if same asset as Speed Boat 1 or separate vessel.
WL-EMP-0031 | Dulip Priyankara — work permit still processing. Cannot operate any vehicle until cleared.
All vessels | Permit and insurance expiry dates missing. Collect from actual documents and fill Document Vault.