## Sheet1
Heavy Equipment Department – Machine Status Update
As of 14/05/2026
Site | Machine | Current Issues | Current Action / Status | Pending Requirements / Approvals
Muthaafushi | Komatsu PC350 (Low Bed) | Boom steel bush requires replacement | Pipe material request raised through Ziyad for fabrication of new bush. Pending finance processing/payment approval. Machining to be carried out at Thilafushi before dispatch. | Awaiting finance clearance and reconfirmation of exact machining measurements/specifications from site.
Muthaafushi | Kobelco SK380 (High Bed) | 1. Battery replacement required with related wiring, lugs, clamps, etc. 2. Hydraulic tank outer door hinges damaged. 3. Cabin side glass damaged. | Initial maintenance/electrical items list received from site. Perspex sheet requested as temporary cabin side replacement solution. Machine-related items being segregated from general site/workshop requests. | Awaiting exact battery specifications, cable sizes, lug/clamp specifications, Perspex dimensions, and hinge repair/fabrication details from Sampath/site team before sourcing.
Muthaafushi | Volvo A40G Dump Truck | Door glass broken | Replacement sourcing under discussion with Dubai Al Dahr. Matter coordinated between management, Ziyad, and myself. | Awaiting sourcing options and management/director approval.
Bodufinolhu | CAT 745C Dump Truck | 1. AC and start motor power supply directly connected. 2. Rear tyre damaged. | As advised by Lakmal, electrical setup requires proper programming/rectification to acceptable operational standards. Technical support/supplier options being explored. Tyre sourcing ongoing through Dubai Al Dahr. Samples/specifications already shared. | Awaiting technical clarification from site regarding electrical rectification scope and director approval for tyre sourcing from Dubai supplier.
Bodufinolhu | CAT Loader | No issues reported | Machine operational. | Nil
Bodufinolhu | Komatsu PC350 (Low Bed) | Hydraulic system slow. Hydraulic pump replacement required. | Machine operational. Dubai Al Dahr has quoted reconditioned hydraulic pump. | Awaiting management/director approval to proceed with sourcing.
Bodufinolhu | Komatsu PC350 (High Bed) | 1. Hydraulic system slow. 2. Hydraulic pump replacement required. 3. Engine overheating after several hours. 4. Head gasket replacement required. | Second hydraulic pump currently being sourced through Dubai Al Dahr. Additional technical clarification requested from site/mechanic regarding gasket requirements. | Awaiting sourcing options, technical specifications, and management/director approval.
Additional Department Updates
Item | Status
Machine-related maintenance/tool/material requests | Consolidated list received from MF/BF sites and currently under segregation into machine-related, workshop, operational, RO/electrical, and contractor-related requirements.
Specifications requested from site | Exact specifications requested for batteries, cables, lugs, Perspex sheet dimensions, bucket shims, fabrication items, compressor requirements, and welding/fabrication support items.
Compressor dispatched to MF | Previously dispatched compressor reported damaged and currently being returned to Thilafushi for repair before re-dispatch to site.